ChildFund International

Humanitarian Situation Report [21]

COVID-19 – [Honduras]

[Rodrigo Bustos, Country Director, rbustos@childfund.org]

[Week of Dec 10 2020]

FOR UPDATES, PLEASE HIGHLIGHT UPDATED SECTIONS IN RED

Part 1: The Overall Situation

COUNTRY

| Total Number of COVID-19 Cases Reported (Udated 8/11/2020) | Number of Deaths | Number of Cases Recuperated |
| --- | --- | --- |
| 111,707 | 2,950 | 49,781 |
| SOURCE: https://www.arcgis.com/apps/opsdashboard/index.html#/bda7594740fd40299423467b48e9ecf6 |  |  |

ChildFund-supported areas (Provide only if you have reliable data on this. You can report on a consolidated  basis or by program state/region/province/etc. if you have this detail.)

| Geographical area (country or state/region/province | Total Number of COVID19 Cases Reported | Number of Deaths | Number of Cases Recuperated |
| --- | --- | --- | --- |
| Francisco Morazán | 274 | 1 | 227 |
| Comayagua | 29 | 2 | 6 |
| Santa Bárbara | 2240 | 70 | 1491 |
| Cortés | 6079 | 181 | 2405 |
| Copán | 1578 | 52 | 1002 |
| Yoro | 3250 | 53 | 951 |
| SOURCE: National Ministry of Health or other reliable source |  |  |  |

The cases reported in the previous table only show information from the municipalities where we have intervention with grant funds and Grants.

http://dataintelligence.azurewebsites.net/Datacovidhn/dashboard/nacional#contenedorIFrame

Souce: https://www.elheraldo.hn/interactivos/1381569-529/coronavirus-honduras-mapa-casos

- Any relevant background information about areas affected.

Host government posture: Have they declared a state of emergency and/or requested outside assistance? Which nationwide measures has the government taken, e.g., limitation on meetings, internal travel, school closures etc.

What responses has the government put into place to address the health crisis and/or the economic impact?

What travel restrictions has the government put in place for travelers entering the country?

- February 26, 2020, Official declaration of dengue and COVID 19 health emergency and 110 million lempiras to address the emergency (Phase 1).

- March 11, 2020, Official communication of the first two COVID 19 cases (Phase 2), one in Tegucigalpa that arrived from Spain on March 4, and another in San Pedro Sula that arrived from Switzerland on March 5.

- March 3, 2020, National school closures.

- March 15, 2020, Suspension of public and private sector work with exceptions and closure of public parks.

- March 16, 2020, Mobility restrictions in the most affected cities: Tegucigalpa, San Pedro Sula.

- March 16, 2020, Curfew in Choluteca.

- March 17, 2020, Curfew in Tegucigalpa, San Pedro Sula, and La Ceiba

- March 20, 2020, National curfew until March 29, 2020

- March 21, 2020, Measures for migration control (closure of commercial flights)

- March 25, 2020, Banking and Financial Agency open schedule from 9 to 4 pm on Monday, Wednesday and Friday.

- March 26, 2020, Official report of the first death in Honduras (San Pedro Sula, Cortés).

- March 26, 2020, The Ministry of Labor decrees that companies and employees can reach agreements to take the days not worked due to the COVID 19 crisis account of vacation.

- March 29, 2020, Measures for the segmented circulation of the population according to the termination of their identity cards.

- March 30, 2020, New emergency measures. Curfew extended to April 12.

- April 1, 2020, validity of the curfew for supermarket, pharmacy and gas stations, Monday, Wednesday and Friday. Pulperías and Mercaditos open every day in neighborhoods and neighborhoods.

- April 5, 2020, Prohibits the transfer from one municipality to another, unless it carries a Safe-conduct. Food transport units must have biosecurity measures.

- April 6, 2020, guarantee restrictions for an absolute curfew for the department of Cortes and the municipality of El Progreso.

- April 7, 2020, CONATEL and telecommunications operators, in consensus, operators the continuity of services for all Hondurans people.

- April 8, 2020, New emergency measures. Curfew extended to April 19.

- April 15, 2020, Transparency Portal for the emergency by Covid-19

- April 19,2020, It was determined to extend the current absolute curfew, from Sunday 19 to Sunday April 26.

- April 22,2020, The state of exception for Colón, Cortés and El Progreso, Yoro extends until May 1.

- April 26,2020, Notice to: Colón, Cortés, El Progreso, Yoro and Las Vegas, Santa Barbara, remain in the absolute curfew.

- April 26,2020, It was determined to extend the current absolute curfew, from Sunday, April 26 to Sunday, May 03.

- May 3, 2020, Absolute curfew extended until May 17 and circulation restricted to one digit per day

- May 6, 2020, absolute curfew for El Progreso, Yoro and Las Vegas, Santa Barbara from Wednesday May 6 at 11:00 pm until Sunday May 10 at 11:00 pm.

- May 10, 2020, Absolute curfew still in effect.

- May 24, 2020, It was determined to extend the current absolute curfew, from Sunday, May 24 to Sunday, May 31.

- May 31, 2020, it was determined to extend the curfew from Sunday, May 31 to Sunday, June 7, only people whose identity number ends from 1 to 5 will be able to circulate Monday to Friday, respectively Saturday and Sunday, remains absolute.

- June 7,2020, Red Alert extended to june 14 only people whose identity number ends from 6 to 0 will be able to circulate Monday to Friday, respectively Saturday and Sunday, remains absolute.

- June 14, 2020, Red Alert extended to june 28 only people whose identity number ends from 1 to 5 will be able to circulate Monday to Friday, respectively Saturday and Sunday, remains absolute.

- June 21, 2020, Red Alert extended to june 28 only people whose identity number ends from 6 to 0 will be able to circulate Monday to Friday, respectively Saturday and Sunday, remains absolute.

- June 28, 2020, Red Alert extended to july 12 only people whose identity number ends from 1 to 5 will be able to circulate Monday to Friday first week, respectively Saturday and Sunday, remains absolute.

- June, 28,2020, Restriction on the mobility of vehicles according to the termination of the last digit license plate.

- June, 28, 2020, the use of face masks is mandatory.

- June, 29, 2020, Suspension of the circulation notice for the last digit of the car registration.

- July, 5, 2020 Still Red Alert extended to july 12 only people whose identity number ends from 6 to 0 will be able to circulate Monday to Friday, respectively Saturday and Sunday, remains absolute.

- July, 12, 2020 Still Red Alert extended to july 19 only people whose identity number ends from 1 to 5 will be able to circulate Monday to Friday, respectively Saturday and Sunday, remains absolute in the Distrito Central,San Pedro Sula,Olancho, Choluteca, Atlántida, Comayagua, Santa Bárbara,Lempira y Colón still remains in phase 0.

- July, 19, 2020  That, it was determined to maintain the absolute curfew throughout the Honduran territory, from Sunday, July 19 at 09:00 pm to Sunday, July 26 at 11:00 pm; and continue with Phase I of the smart opening process except for the Central District, San Pedro Sula, Olancho Choluteca, Atlántida, Comayagua, Santa Bárbara, Lempira and Colón.

- July, 26, 2020 That, it was determined to maintain the absolute curfew in the entire Honduran territory, from Sunday, July 26 at 09:00 pm until Sunday, August 2 at 11:00 pm; and continue with Phase I of the smart opening process except for the Central District, San Pedro Sula, Olancho Choluteca, Atlántida, Comayagua, Santa Bárbara, Lempira and Colón

- July, 29, 2020 Council of Ministers approves to retake phase 1 for economic reactivation throughout the country.

- August , 2, 2020 Still Red Alert extended to july 19 only people whose identity number ends from 1 to 5 will be able to circulate Monday to Friday, respectively Saturday and Sunday .

- da August, 21, 2020, New circulation calendar nationwide, each number from 1 to 0 will be changed according to the progress of phase 1 of the economic opening and the process of Covid-19 cases.

- September, 21, 2020 The government authorizes two-digit circulation per day from this Mon y, September 21, until October 4.

- October 2, The Government of Honduras declared the emergency by ETA on November 2, 2020 through Executive Decree Number PCM-109-2020 published in the La Gaceta newspaper.The Central Government and humanitarian aid from civil society organizations (NGOs, United Nations, private companies, among others) are prioritizing support for the north coast of the country, the area most affected by tropical storm ETA.As of

- November 11, preliminary information indicates that the Ministry of Health will allocate 100,000 rapid tests for the shelters, the BCCIC has offered 250 million dollars for reconstruction in Honduras, the WFP will send 1,500 tons of food for those affected.

- This has increased the risk of contagion from Covid 19

- October, 11,2020 The Secretary of Security and SINAGER, communicated an absolute curfew from Sunday, October 11 to November 8, being suspended by the Tropical Storm ETA since November 3.

- November, 16,2020. The Secretary of the Interior, Justice and decentralization suspends work due to the passage of huracan IOTA on tuesday 17 and wednesday 18 november 2020 .

- December, 6, 2020. The Secretary of State in the Security office through the National Police of Honduras, in relation to the process of recovering the damages caused by the recent natural phenomena that affected the country, communicates to the public. That a red alert is maintained in throughout the Honduran territory, for which humanitarian assistance and reconstruction work is carried out.

What responses has the government put into place to address the health crisis and/or the economic impact?

- March 20, 2020, Food distribution plan for 3.2 million people

- March 20, 2020, Economic measures package

- March 18, 2020, Procurement of biomedical equipment (from New York)

- March 27, 2020, Government decrees maximum prices for a basic food basket.

- March 29, 2020, Extension of the Honduras Solidaria Program for the municipalities.

- March 30, 2020, Tax measures for businesses and employees to save jobs.

- April 14, 2020, COPECO, reported purchases made, in the context of the emergency due to the COVID-19 pandemic

- April 18,2020, Procedure for companies that wish to avail themselves of the law to assist the Productive Sector and Workers in the face of the effects of the Pandemic caused by COVID-19.

- May 18, 2020, Absolute curfew extends THROUGHOUT THE COUNTRY, from Sunday, May 17 at 11:00 pm, until Sunday, May 24, 2020, at 11:00 pm.

- June 7, 2020, Phase I opening statement.

- June 21, 2020, Press release, that due to the lack of compliance with biosafety protocols, the increase and saturation of hospital capacity was determined that from this Sunday June 21 at 9:00 pm until Sunday June 28 at 11:00 pm the suspension of the Phase I opening statement in Tegucigalpa city.

- June,28,2020, San Pedro Sula and Tegucigalpa remain in phase 0 of reopening due to the increase in cases of COVID 19.

- July, 14, 2020, The government demands from all its institutions that the issue of accountability and transparency is mandatory, it is a priority.

- July, 28, 2020 In the case of public transport, starting Monday, August 1 of this year, pilots will be underway for its orderly reopening through the Honduran Institute of Land Transport.

- August, 9, 2020 The Government of the Republic of Honduras, in compliance with the opening process in Phase 1 of the Economic Sector in most of the country and with the purpose of guaranteeing the attention to the user of State institutions.

- September, 21, 2020 Shopping centers will be enabled to be open, with exceptions in fast food. Likewise, public transport will gradually operate again, taking into account the units that carried out the piloting in phase 1.

- October, 04, 2020 The commercial and economic system is authorized to attend to the population, in this way it continues with Phase I to the municipalities that were in Phase 0, the rest of the country in Phase 2 of the gradual and Responsible Opening.

What travel restrictions has the government put in place for travelers entering the country?

- Land: Entry and exit of cargo transporters, Hondurans, residents, and diplomats undergoing biosecurity measures

- Maritime: only for cargo vessels, crew not authorized to disembark

- Air: Closing for commercial flights.

- March 29, 2020: San Pedro Sula and Tegucigalpa airports open for international flights, with restrictions.

- April 14, 2020, The closure of operations of international airports is maintained until Sunday, April 19

- August, 2 2020 Airports will begin operations the first week of August, the first 15 days will be local flights, then international flights will be carried out with some restrictions.

- August, 16, 2020 Activation of international air transport.

Information source: https://covid19honduras.org/?q=Comunicados

Part 2: The Situation in Areas Where ChildFund Works

| Partner Organization (Use Salesforce identifying code/name.) | # of Enrolled and Sponsored Children |  | COVID19 Cases Reported in ChildFund Communities (Y/N/Unknown) Provide number if available. | Number of Enrolled Children Reported with COVID19 (If available.) | Number of enrolled children diseased as result of COVID19 /Tropical Storm ETA |
| --- | --- | --- | --- | --- | --- |
|  | Sponsored | Enrolled |  |  |  |
| 1510001/ADAL-Lepaterique Area Development Association | 5214 | 7153 | y | 6 | 0 |
| 1510003/CASM- Menonita Social Action Commission | 3777 | 4904 | y | 0 | 0 |
| 1510005/ADASBA Santa Barbara Area Development Association | 5502 | 6917 | y | 4 | 1 |

Our Local partner ADASBA reports a new child who tested positive for Covid-19 and is in stable condition. The Local Partner keeps close monitoring to her condition and needs.

The children reported positive last month have fully recovered along with their relatives.

Child deaths: List any sponsored child (with Partner organization and child ID from salesforce) diseased as a result of COVID19. (Note: These need to be reported immediately following the regular sponsorship protocols.)

| Partner Organization (Use Salesforce identifying code/name.) | What is the status of the program/sponsorship processes (operational/suspended)? |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Program Implementation | CVS | M&E Level 2 | Enrollment /Disaffiliation | Sponsorship Communication | DFC |
| 1510001/ADAL-Lepaterique Area Development Association | Partially Operational | Suspended | Suspended | Partially Operational | Partially Operational | Operational |
| 1510003/CASM- Menonita Social Action Commission | Partially Operational | Suspended | Suspended | Partially Operational | Partially Operational | Operational |
| 1510005/ADASBA Santa Barbara Area Development Association | Partially Operational | Suspended | Suspended | Partially Operational | Partially Operational | Operational |
| etc. |  |  |  |  |  |  |

Note: As a global measure, all sponsor visits have been suspended.

Tropical storm ETA severely hit the country the first week of November leaving a lot of devastation mainly on the northern and western part of the country. Several communities where ChildFund works were affected with flooding and landslides. Access to communities were blocked due to the destruction of bridges, main and secondary roads and landslides. Several of our enrolled children and families have been affected to the point that we have already reported death of one of our sponsored children.

As expected, we have experienced delays on child correspondence.   For Local Partners ADASBA and CASM they are only processing DFCs and trying to reply to Child Welcome requests when possible. All Sponsor correspondence is suspended for the moment due to the difficult access to the community and families.

What issues are children in these areas facing (food shortages, safety concerns, school closures, etc.)?                                                                                                                                                               As mentioned above, due to government lockdown, schools are closed, and children are staying at home where they are doing some schoolwork.

- Child protection risks caused or exacerbated by a crisis.

The situation of confinement and overcrowding that the majority of the families live in could increase the risk of physical, psychological and sexual violence; especially on girls and women living in poverty, discrimination and exclusion.

Part 3: ChildFund’s Response

3.a. Overall

- Who is or will be leading/managing the response?

Country Team:

- Rodrigo Bustos, Country Director, Team leader

- Daysi Kocchiu, Partnership Portfolio Manager, Partner Coordination

- Ana Handrez, Sponsorship Engagement and Retention Manager

- Patricia Betancourt, Protection Specialist, Protection Focus

- Zorayda Zelaya, Advocacy and Communication Specialist, Gender and Communication

- Kelvin Fúnez, Program Officer, Emergency Focal Point, Monitoring

- Allison Iraheta, Business Development Specialist

Planned, desired or ongoing response -inside or outside current operational areas

- Permanent meetings with the Humanitarian Network for analysis of the viability of the cash transfer mechanism as a strategy for food security and its implementation in our work area; permanent updating of the OCHA 3W page.

- Approach at the local level, through the three implementing partners (ADAL, ADASBA, and CASM)

  - Permanent meetings with local governments and intersectoral tables for local situation analysis, identification of response capacity by the health sector and coordination of preparedness actions.

  - Monitoring of the situation of children through the communication networks organized by the local partners.

  - Programmatic response based on the ChildFund Minimum Standards and Life Stage and Child Protection Technical Guidance.

  - Support in food security (non-perishable basic food) and WASH (hygiene kit) to targeted families, through a mechanism, to be defined based on criteria of access and availability of financial channels and product suppliers (Cash transfer or voucher).

  - Communication to families with key messages on measures to avoid infection, respect for stay at home measures, protection of children especially girls in the family in this situation of crisis and isolation.

  - Country Office COVID 19 Emergency Response Plan prepared and sent to Regional Director. This was prepared in coordinated action with the Guatemala Country Office. It addresses two results of the Results Framework proposed by the Regional Office of the Americas. The first result was oriented towards subsistence support for targeted families, for which the selection criteria have been defined, the subsidy budget reoriented for it, and the mechanisms for accountability by local partners.

  - The Honduras Country Office and our Local Partners have updated the Response Pandemic COVID 19 Plan, First Quarter FY21 (July – September 2020), Result 1. We have projected the support to 5,687 additional families.  We aim to achieve a coverage of 100% of families with enrolled children with at least one CVA from April to September 2020.

How is ChildFund linked with humanitarian coordination structures, i.e., in which clusters or working groups do we participate? The most recent/next meeting and who is representing ChildFund? Donor meetings we have attended, or missions that we are aware of related to the response?

- Participation in meetings of the Humanitarian Network coordinating actions with other members, and with the central government in terms of piloting direct support to families in communities with a high incidence of COVID 19.  OCHA 3W COVID 19 page update.

- Consultations with organizations in the Humanitarian Network that manage Cash Transfers, to learn about methodologies, delivery mechanisms, tools for analysis, among other points.

- Advocacy and Communication Specialist and Protection Specialist will be representing ChildFund in the sub-clusters of Child Protection, of the United Nations System in Honduras, with the objective of coordinating interventions to respond in an organized manner to the protection needs of children.

- Participation in meetings to elaborate the action plan of the sub-clusters of Child Protection, of the United Nations System in Honduras. ChildFund´s activities were included in the protection mapping of the sub-cluster. ChildFund is contributing with in the development of the sub-cluster advocacy plan.

Ongoing interventions:

- Communication of key messages through social and community networks to families and communities. This week has emphasized the issues of protection and care of children in the family, self-identification of COVID 19 symptoms, reference route in case of suspected infection.

- Through the Decentralized Health Project in the coverage area of the ADAL Partner:

  - Distribution of 2,000 hygiene kits for the most vulnerable population (pregnant women, people with chronic diseases, NACE children, among others).

  - Distribution of P&G sachets to 7,000 families for water purification.

- Consultation with local partners on the criteria to be considered for decision-making (local supply of products, restrictions on the mobilization of the population, time for implementation, risks/security, financial services available, dynamization of the local economy).

- Accompanying local partners in preparing the programmatic response based on ChildFund Minimum Standards and Life Stage and Child Protection Technical Guidance for April, May and June 2020.  A technical matrix has been developed and provided to local partners to guide the programming of sessions by Programmatic Model (Format 1).

- Development and delivery of guidelines for updating the three local partners' COVID 19 Emergency Response Plan which includes a format for programming, budgeting and monitoring of activities, and identification of funds to be allocated to support food security and WASH (Format 2).

- Through our CASM local partner, Honduras CO started the execution of the subsistence support component of our Response Plan by delivering vouchers to 34 families and species to 458  families, a total of 492 families with enrolled children from the municipalities of Atima, Trinidad and San José de Colinas, Santa Barbara Department.  The support to the 458 families was complemented by a delivery in species of similar value made by the “Honduras Solidaria” Government Program, thus achieving support for the 1,894 family members with a comprehensive kit made up of basic food and hygiene products that complement their diet for approximately 1  month. The delivery of subsistence support was complemented by oral and written information (brochure) that was provided to each participating family on biosafety protection measures to prevent the spread of COVID 19 in their homes.

- Participated in the "Workshop on assistance in communities, work with population / communities at risk of violence and security of the humanitarian worker".

With this workshop, which seeks to support the different sectoral working groups that are activated, it is intended to provide support through technical advice through the experience of the members of the Humanitarian Country Team. For this, the following topics were developed:

  - Humanitarian Assistance in communities

  - Work with population / communities at risk from violence

  - Humanitarian worker safety

The workshop shared tools, good practices and lessons learned on these topics and how to help protect the transverse sea in different lines of work. At the end of the workshop, a space was created for case studies where the participants shared challenges that we did not face and how the Protection Group guides us.

Through our three local partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering cash transfer, in kind integral support and in kind hygiene kit to a total of 3,865 families (18,851 persons) with enrolled children from Santa Barbara and Francisco Morazán Departments:

- Cash transfer and in kind hygiene kits to 528 families (2812 persons), total US$21,209.15 / $36.58 CT each family and $3.585 each in kind hygiene kit.

- In kind integral support  (subsistence and hygiene kit) to 918  families (4154  persons);  total $35,932.95  / $39.14 each family).

- In kind integral support 50% (subsistence and hygiene kit) to 364 families from Atima, Santa Bárbara (1,587 persons); $7,098.21 / $19.50 each family). This support was complemented by a delivery in species of similar value made by the “Honduras Solidaria” Government Program.

- In kind hygiene kits to 2,055 families (10,298 persons); total US$ 7,367.17 / $3.585 each family.

The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

Through our Acción Honduras local partner, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering cash transfer and in kind hygiene kit to a total of 849 families (4,179 persons) with enrolled children from Francisco Morazán Department:

- Cash transfer and in kind hygiene kits to 2 families (10 persons), total US$ 80.39 / $36.59 CT each family and $3.61 each in kind hygiene kit.

- In kind hygiene kits to 847 families (4,166 persons); total US$ 3,059.72 / $3.61 each family.

The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

Through our Acción Honduras Local Partner, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Voucher and in kind hygiene kit to a total of 410 families (2,140 persons) with enrolled children from Francisco Morazán Department.

The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

Through our ADASBA and Acción Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering cash transfer, voucher and in kind hygiene kit to a total of 1,160 families (5,622 persons) with enrolled children from Santa Bárbara and Francisco Morazán Departments.

The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

- Through our ADASBA and CASM Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering voucher, in kind integral support and in kind hygiene kit to a total of 417 families (1,934 persons) with enrolled children from Santa Bárbara Department.

The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

- Preparation of AOP FY21 Local Partners guidelines with emphasis of Quarter One (Continuous Emergency Response Plan Pandemic COVID 19.

Project “Safe Water for Children in Honduras”, through the Decentralized Health Project will distribute P&G sachets for water purification to 7,000 families of Curarén, Alubarén and Reitoca municipalities; and La Libertad and San Miguelito Municipalities coordinating efforts with ADRA organization. In alliance with Oxfam, also will distribute P&G sachets to 1,240 families of 6 municipalities in Lempira Department, and 2 municipalities in Valle Department.

In kind executed (June 1  – June 7, 2020). Through our ADASBA Honduras Local Partner, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering in kind integral support to a total of 219 families (1,044 persons) with enrolled children from Santa Bárbara Department.

Voucher and in kind executed (June 8  – June 14, 2020). Through Acción Honduras, CASM and  ADASBA Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering voucher and in kind integral support to a total of 2,869 families (11,089 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments.

Cash transfer and in kind executed (June 15 – June 2, 2020). Through Acción Honduras, CASM and  ADASBA Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering cash transfer and in kind integral support to a total of 1,900 families (8,720 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments.

Food baskets and hygiene kits supports (June 22 – June 28, 2020). Through  CASM and  ADASBA Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Food basket and Hygiene kit (integral support) and only Hygiene kit to a total of 683 families (2,812 persons) with enrolled children from Santa Bárbara Department.  It is important to clarify that the 75 families that this week are being supported with hygiene kits have already received support with the Food Basket in April 2020.

Due to the advance of the COVID 19 infection in Lepaterique Municipality (Francisco Morazán Department), Acción Honduras Local Partner and CF decided to reschedule the cash transfer delivery  (624 families of Lepaterique), so as not to expose them to the risk of infection.

Voucher support executed (June 29 – July 05, 2020). Through  Local Partner Acción Honduras, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Vouchers to a total of 59 families (610 persons) with enrolled children from Francisco Morazán Department.

Cash transfer, Voucher and Food baskets support executed (July 06 – July 31, 2020). Through Local Partners Acción Honduras, ADASBA and CASM, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Cash transfers to a total of 624  families (3,222 persons), Vouchers to 802 families (3,686 persons) and food baskets to 1,351 families (6,096 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments (Total: 2,777 families, 13,004 persons, $ 76,652.84).

Cash transfer, Voucher and Food Baskets support executed (August 1 – 31, 2020). Through  Local Partners, CO continue the execution of the subsistence and hygiene support component (Result 2) of our Response Plan by delivering Cash transfers and voucher to 472 families (2,430 persons) and food baskets to 1,717 families (7,986 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments (Total: 2,189 families, 10,416 persons, $  66,584.49).

3.b. Program Response

Please organize your program response report as per the 4 objectives included in our global response plan. You can add an additional category if you have response activities planned or executed that do not align with these objectives. For each objective use the questions below to guide your report.

- What kind of response activities or interventions have been executed? What support items are needed or have been collected/distributed?

- What is the current progress of implementation vs. the established response plan?

- Who are we partnering or collaborating with to provide our response?

- What kind of response activities are you still planning for the coming period?

Key messages disseminated by local partners to communities and families in our coverage area on COVID 19 based on existing content and material on the websites of reference organizations such as WHO, UNICEF, Ministry of Health of Honduras, ChildFund, using social networks (Facebook, WhatsApp) and mobile phones.

Translation and socialization of ChildFund International's programmatic guidelines (Minimum Standards and Technical Guide) with local partners, development of a complementary tool for programmatic adaptation of the quarter.

Preparation of guidelines and instruments for updating the Emergency Response Plan of local partners and its socialization with three partners.

In order to identify alternative ways for Program Models Delivery (including communication plan messages), with an emphasis on non-face-to-face ways, the country team in joint action with local partners has started a media mapping throughout the ChildFund coverage area with both sponsorship and grant funds.  The mapping consider: access to media such as local and / or regional Cable TV, national, regional and community radio, internet connectivity, cellular signal connectivity, national newspaper at the community level; as well as the electrical energy production systems and access to devices by families, youth and communities such as computers, radio, TV, analog phones, smart phones.

We have developed a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine. This booklet was printed and is being delivered in the most remote communities. It will be used by parents, since in these moments of emergency it requires not to forget about CAY in all their pursuits and concerns. This material is easy to read, with illustrations, short phrases, adopted language to the region and with necessary information.

A radio campaign has been started on local radiophone media, with messages about the importance of taking care and assisting CYA during this situation of emergency, emphasizing on possible reactions that CYA could manifest during the Covid-19 emergency.

The 30 of April we sign the new grant entitled “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood " with an amount of $752,442, in which for the coming months we will support vulnerable families with children under 6 years old in the departments of Santa Bárbara, La Paz, Intibuca, Lempira, Ocotepeque, Copán. This response consist of delivering 1,500 usbs containing information in  the necessary measures in how to prevent Covid-19.

The new booklet is ready to be delivered to the beneficiary population.

Local partners perform their radio programs with prevention and protection messages.

As part of the communication plan, local partners share the referral routes for cases.

The transmission of radio theaters with themes focused on the care of children during the crisis begins.

The production of new radio theaters begins with different themes such as the route of referral of cases, types of violence, signs in abused children, gender roles, care during the crisis caused by covd19.

A booklet with information on activities to do with children is already being distributed along with food delivery.

A media mapping has been carried out to determine the existence of internet, radio and television connectivity in the execution areas.

In association with local partners, we have developed infographics for child protection on psychological first aid for children and psychological health guides to cope with COVID-19.

Prevention, care and childcare messages are being transmitted on 6 different radios.

5 new radio theaters are ready to be published, which their topics are: protection, gender, referral routes, safety measures etc.

5 new radio theaters are published in 6 different radios, which their topics are: protection, gender, referral routes, safety measures, etc.

A media mapping is going to be carried out to determine the existence of internet, radio and television connectivity in every enrolled family in the execution areas. This information will be the basis for the initiatives of delivery to families by Sponsorship and Programs initiatives.

ChildFund’s Global Response Plan

To help children and families protect themselves from COVID-19, we are installing community, handwashing stands; educating communities about symptoms, hygiene measures and where to get tested or treatment; and distributing soap, hand sanitizer, gloves and masks to families and frontline, health workers. For children who are being treated for COVID-19 or are subject to quarantine measures, we are creating child-friendly spaces with age-appropriate toys and reading matter.

ChildFund’s Global Response Plan

To help children and families protect themselves from COVID-19, we are installing community, handwashing stands; educating communities about symptoms, hygiene measures and where to get tested or treatment; and distributing soap, hand sanitizer, gloves and masks to families and frontline, health workers. For children who are being treated for COVID-19 or are subject to quarantine measures, we are creating child-friendly spaces with age-appropriate toys and reading matter.

3.b.1. Stop COVID-19 from infecting children and families

Through the Decentralized Health Project in the coverage area of the ADAL Partner, WASH support to 2,000 people (pregnant women, people with chronic diseases, NACE children, among others) and 7,000 families with water purification sachets.

On April 17th, we delivery more than 10 thousand hygiene kits , with a approximate cost of USD.32,038.5 dollars, to the Direction of Adolescence and Family (DINAF). These kits will be used by children, youth and teenagers who will return to the country after a deportation process, in total precariousness and many of them who were unaccompanied. Thanks to this important donation these children, youth and adolescents will now have the possibility to adopt the hygiene measures that allow avoiding the virus contagion. The hygiene kits will be distributing in the principal cities of the country, San Pedro Sula and Tegucigalpa, which are the most affected places by this illness and it is a determinant resource in this moment to preserve health to those who receive it as from the people around them.

Between April 20 and 21, teams from the National Risk Management System (SINAGER) from 4 municipalities of the Department of Santa Bárbara were supported by ChildFund to improve their  biosecurity conditions. These teams coordinate with our local partners the Response to the Emergency in  ChildFund intervention zone. ChildFund provided hygiene kits and biosafety equipment for the value of $ 3,085.

The 30 of April we sign the new grant entitled “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood ", with an amount of $752,442, in which for the coming months we will support vulnerable families with children under 6 years old in the departments of Santa Bárbara, La Paz, Intibuca, Lempira, Ocotepeque, Copán affected by the emergency with a hygiene kit. We will deliver 7,000 hygiene kits for the prevention of COVID-19 and other diseases such as dengue fever and diarrhea.

In order to curb the spread of this virus and consider the rights and needs of the most vulnerable people, we presented a proposal to the Canadian Fund Local Initiative of Honduras, Costa Rica, Nicaragua "To strengthen prevention, detention and care measures for patients who are suspected and/or positive for Covid-19 in rural communities by providing basic medicines for patients with chronic diseases, personal protection equipment for health workers and to raise awareness in rural communities about how to prevent the spread and what to do in cases of being suspected of Covid-19" in the communities of Alubaren, Curaren, Reitoca, La Venta and Lepaterique in the department of Francisco Morazán.

September 10th , ChildFund Honduras signed an agreement with the Ministry of Health for the project“Health  Immediate Public Health Response Program to Contain and Control Covid-19 and mitigate its effect on service delivery in Honduras (RISP-HO)”. The project general objective is to contribute to the strengthening of the First Level of Care networks (Hospital Escuela Universitario, Health Region Metropolitan, and Healthe region for Francisco Morazan), facilitating timely attention to the population through support for strategic and operational epidemiological surveillance actions for preventing the spread of the disease, containing transmission, improving access and care of suspected and positive cases of COVID-19 in Honduras. The project aims the following expecting outcomes:

For  the Health Region of Francisco Morazán:- Have a triage supervisor team, equip health facilities and triage centers with personal protection equipment antiseptic medication for oral use, Azithromycin, Ivermectin and Zinc. (MAIZ), 10,000 rapid tests for the detection of Covid-19 in suspect patients for the 103 health establishments and 27 triages.

For the Health Region of the Metropolitan - Form 6 new regional rapid response teams and strengthen 6 local rapid response teams with emergency support personnel. In order to support the 77 current Rapid Response Teams (13 regional ERRs to support the 64 local ERRs), where microbiologists and technicians from the different CIS will be concentrated to give a timely response made up of general practitioners, ASA.

For the Hospital Escuela Universitario (Public Hospital) :Improve the capacity of care for patients with chronic diseases, acute and Covid-19 that demand the service of the hospital (Currently there have been medical personnel who have been disabled due to the same disease of the Covid-19), equip the hospital with medication and PPE.

The 15 of October we signed an agreement for the IV phase for the project “Clean Water for Honduras” with emphasis in Covid-19 prevention, this phase will have components such as multiple aspects geared towards COVID-19 prevention (clean water, hand washing stations for schools and health clinics, biosecurity kits for volunteers, Covid-19 prevention campaign, additional sachets with other nonprofit organizations, etc.)

ChildFund’s Global Response Plan

To ensure that the most vulnerable families can keep food on the table, pay rent and cover other basic needs, we are providing cash for those families most needing this support, such as those who have lost their income because of COVID-19, child or elder-headed households, and/or households affected by disability or chronic illness. Where possible, we are distributing food and basic household items directly, carefully abiding by COVID-19 protection measures

ChildFund’s Global Response Plan

To ensure that the most vulnerable families can keep food on the table, pay rent and cover other basic needs, we are providing cash for those families most needing this support, such as those who have lost their income because of COVID-19, child or elder-headed households, and/or households affected by disability or chronic illness. Where possible, we are distributing food and basic household items directly, carefully abiding by COVID-19 protection measures

3.b.2. Ensure that children get food they need

3.b.2. 1. Cash Transfers and vouchers

-Is your CO planning or implementing cash transfers or vouchers as part of COVID19 response?

Yes

The distribution plans of the subsistence support to the prioritized families are ready at the local level through our local partners, for their execution as of Wednesday April 22,2020. The support of more than 5,205 families with an average value of $ 40.00 per family (Cash transfer, voucher and in kind) between the months of April to June 2020.

- If so, brief description of progress to date.

Selection of beneficiary families:

- Criteria for the selection of beneficiary families defined in discussion with local partners.

- Value of subsistence support per family defined in $ 40 (L. 1,000) for two months. It is an estimated value by organizations of the Humanitarian Network and the Honduras Solidarity Program of the government of Honduras.

- Estimated budget to be reoriented to support for family subsistence, monthly projection of the execution defined with each local partner.

- Listings of families targeted according to criteria, estimating 5206 families, equivalent to 39.6% of the total families with enrolled children.

Commodity supplier market analysis

- Supplier market analysis carried out at the level by two of the local partners (Acción Honduras and ADASBA). In general, to date, there is a supply of basic products at the local level.

Mapping of financial mechanisms

- Mapping of cash delivery mechanisms carried out at the local level by two of the three local partners (ADASBA and Acción Honduras).

- We expect to initiate the cash transfer next week

- For the first support, cash transfer (Acción Honduras), Voucher and species (CASM and ADASBA) will be mechanism used.

The distribution plans of the subsistence support to the prioritized families are ready at the local level through our local partners, for their execution as of April 23, 2020. The support of more than 5,205 families (39.8% coverage enrolled families) with an average value of $ 40.00 per family (Cash transfer, voucher and in kind) between the months of April to June 2020.

CAV executed (April 22 – 26, 2020). Through our CASM local partner, Honduras CO started (April 22 to 26) the execution of the subsistence support component of our Response Plan by delivering food baskets to a total of 492 families with enrolled children from the municipalities of Atima, Trinidad and San José de Colinas, Santa Barbara Department.  The support to the 458 families was complemented by a delivery in species of similar value made by the “Honduras Solidaria” Government Program. In total, we support 1,894 family members with a comprehensive kit made up of basic food and hygiene products that complement their diet for approximately one month.  The delivery of subsistence support was complemented by oral and written information (brochure) that was provided to each participating family on biosafety protection measures to prevent the spread of COVID 19 in their homes.

| Cash and Voucher/ April 22 – 26, 2020 |  |
| --- | --- |
| Total families | US$ |
| 0 | $ 0 |

| Beneficiaries |  |  |  | Amount transferred (US$) | Mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 492 | 1,894 | 963 | 931 | $16,043.32 |  |
| Detail |  |  |  |  |  |
| 492 | 1,894 | 963 | 931 | $16,043.32 | Food Basket and Hygiene Kit |

*Source:  SIMA Platform, September 10, 2020, M&E CVA Country Office

CVA  executed (April 27 – May 3, 2020). Through  Local Partners, CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Cash transfers to 512 families (2,804 persons) and food baskets to 1282 families (5,741 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments (Total:  1,794 families, 8,545 persons, $  65,175.45).  The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

| Cash and Voucher: April 27 – May 3, 2020 |  |
| --- | --- |
| Total Families | (US$) |
| 512 | $20,604.88 |
| *Sources: SIMA Platform, September 10, 2020; M&E CVA Country Office. Comment: Value includes Cash/Voucher ($36.5853) and kit hygiene ($3.6585): Total unit: $40.24385 |  |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 1,794 | 8,545 | 4,393 | 4,152 | $ 65,175.45 |  |
| Detail |  |  |  |  |  |
| 512 | 2,804 | 1,516 | 1,288 | $20,604.88 | Cash (with hygiene kit) |
| 1,282 | 5,741 | 2,877 | 2,864 | $44,570.57 | Food Basket and Hygiene Kit |

Sources:  SIMA Platform, September 10, 2020; M&E CVA Country Office.

Cash transfers and in kind executed (May 4 – May 10, 2020)

| Cash and Voucher: |  |
| --- | --- |
| Total Families | (US$) |
| 2 | $ 80.49 |
| * Sources: SIMA Platform, September 10, 2020; M&E CVA Country Office. Comment: Value includes Cash/Voucher ($36.5853) and kit hygiene ($3.6585): Total unit: $40.24385 |  |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 2 | 10 | 4 | 6 | $80.49 |  |
| Detail |  |  |  |  |  |
| 2 | 10 | 4 | 6 | $80.49 | Cash (with hygiene kit) |

* Sources:  SIMA Platform, September 10, 2020; M&E CVA Country Office

Honduras CO continue the execution of our Response Plan by delivering Cash and hygiene kit to a total of 2 families (10 persons) with enrolled children from Francisco Morazán Department.

CAV executed (May 11 – May 17, 2020)

| Cash and Voucher: May 11 – 17, 2020 |  |
| --- | --- |
| Total Families | (US$) |
| 30 | $ 1,207.32 |

Comment:  Value includes Cash/Voucher ($36.5853)  and kit hygiene ($3.6585):  Total unit: $40.24385

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 30 | 153 | 72 | 81 | $1,207.32 |  |
| Detail |  |  |  |  |  |
| 30 | 153 | 72 | 81 | $ 1,207.32 | Voucher (with hygiene kit) |

* Sources:  SIMA Platform, September 10, 2020; M&E CVA Country Office.

Honduras CO continue the execution of our Response Plan by delivering Cash and hygiene kit to a total of 30 families (153 persons) with enrolled children from Francisco Morazán Department.

CVA  executed (May 18 – May 24, 2020)

| Cash and Voucher: May 18 – 24, 2020 |  |
| --- | --- |
| Total Families | (US$) |
| 499 | $20,081.71 |
| ** Sources: SIMA Platform, September 10, 2020; M&E CVA Country Office. Comment: Value includes Cash/Voucher ($36.5853) and kit hygiene ($3.6585): Total unit: $40.24385 |  |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism, |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 1,122 | 5,485 | 2,769 | 2,716 | $ 42,120.04 |  |
| Detail |  |  |  |  |  |
| 94 | 335 | 186 | 149 | $ 3,782.93 | Cash (with hygiene kit) |
| 405 | 2,043 | 1,038 | 1,005 | $16,298.78 | Voucher (with hygiene kit) |
| 623 | 3,107 | 1,545 | 1,562 | $ 22,038.34 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020, M&E CVA Country Office

The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

CVA  executed (May 25 – May 31, 2020)

| Cash and Voucher: |  |
| --- | --- |
| Total Families | (US$) |
| 0 | $0.00 |
| *Source: SIMA Platform, September 10, 2020; M&E Country System |  |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 695 | 1,426 | 711 | 715 | $17,315.85 |  |
| Detail |  |  |  |  |  |
| 695 | 2,832 | 1,420 | 1,412 | $17,315.85 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020, M&E Country System

The 28 of May ChildFund International office-EAF approved $25,000 to give continuity to the Country Office COVID 19 Emergency Response Plan reaching to a 4.7% (615 families  with children and youth) in the departments of Francisco Morazán and Santa Bárbara who are experiencing problems of access to basic food and hygiene kit, so that they can improve their livelihoods capacity during this period through one of this two mechanisms: preferable cash transfer or voucher.

Through our ADASBA and CASM Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering voucher, in kind integral support and in kind hygiene kit to a total of 695 families (2,832 persons) with enrolled children from Santa Bárbara Department. The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

CVA executed (June 1 – June 7, 2020)

| Cash and Voucher: |  |
| --- | --- |
| Total Families | (US$) |
| 0 | $0.00 |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism, |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 219 | 1,044 | 514 | 530 | $ 5,138.29 |  |
| Detail |  |  |  |  |  |
| 219 | 1,044 | 514 | 530 | $ 5,138.29 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020. M&E Country System

Through our ADASBA Honduras Local Partner, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering in kind integral support to a total of 219 families (1,044 persons) with enrolled children from Santa Bárbara Department. The delivery of subsistence and hygiene support was complemented by a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine.

CVA (June 8 – June 14, 2020). Through Acción Honduras, CASM and  ADASBA Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering voucher and in kind integral support to a total of 2,869 families (11,089 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments.

| Cash and Voucher |  |
| --- | --- |
| Total Families | (US$) |
| 1064 | $ 42,819.51 |
| *Source: SIMA Platform, September 10, 2020. Comment: Value includes Cash/Voucher ($36.5853) and kit hygiene ($3.6585): Total unit: $40.24385 |  |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 2,349 | 11,089 | 5,670 | 5,419 | $ 72,708.68 |  |
| Detail |  |  |  |  |  |
| 1,064 | 4,964 | 2,522 | 2,442 | $ 42,819.51 | Voucher (with hygiene kit) |
| 1,285 | 6,125 | 3,148 | 2,977 | $ 29,889.16 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020

CVA executed (June 15 – June 21, 2020). Through Acción Honduras, CASM and  ADASBA Honduras Local Partners, Honduras Country Office continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering cash transfer and in kind integral support to a total of 1,900 families (8,720 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments.

| Cash and Voucher: June 15 – 21, 2020 |  |
| --- | --- |
| Total Families | (US$) |
| 11 | $ 442.68 |

Comment:  Value includes Cash/Voucher ($36.5853)  and kit hygiene ($3.6585):  Total unit: $40.24385.

*Source:  SIMA Platform, September 10, 2020

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism (i.e. mobile money, banking system other financial service provider etc, |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 1,666 | 8,720 | 4,399 | 4,321 | $ 38,551.80 |  |
| Detail |  |  |  |  |  |
| 11 | 50 | 28 | 22 | $ 442.68 | Cash (with hygiene kit) |
| 1,655 | 8,670 | 4,371 | 4,299 | $38,109.12 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020

CVA executed (June 22 – June 28, 2020). Through  CASM and  ADASBA Honduras Local Partners, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Food basket and Hygiene kit (integral support) and only Hygiene kit to a total of 683 families (2,812 persons) with enrolled children from Santa Bárbara Department.  It is important to clarify that the 75 families that this week are being supported with hygiene kits have already received support with the Food Basket in April 2020.

| Cash and Voucher: June 22 – 28, 2020 |  |
| --- | --- |
| Total Families | (US$) |
| 0 | $0.00 |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 683 | 2,515 | 1,311 | 1,204 | $ 25,018.04 |  |
| Detail |  |  |  |  |  |
| 683 | 2,515 | 1,311 | 1,204 | $ 25,018.04 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020

Due to the advance of the COVID 19 infection in Lepaterique Municipality (Francisco Morazán Department), Acción Honduras Local Partner and CF decided to reschedule the cash transfer delivery  (624 families of Lepaterique), so as not to expose them to the risk of infection.

CVA support (June 29 – July 05, 2020). Through Local Partner Acción Honduras, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Vouchers to a total of 59 families (610 persons) with enrolled children from Francisco Morazán Department.

| Cash and Voucher |  |
| --- | --- |
| Total Families | (US$) |
| 59 | $ 2,374.39 |
| *Source: SIMA Platform, September 10, 2020, Comment: Value includes Cash/Voucher ($36.5853) and kit hygiene ($3.6585): Total unit: $40.24385. |  |

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism, |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 59 | 610 | 153 | 457 | $ 2,374.39 |  |
| Detail |  |  |  |  |  |
| 59 | 610 | 153 | 457 | $ 2,374.39 | Voucher (with hygiene kit) |

*Source: SIMA Platform, September 10, 2020

CVA executed (July 06 – July 31, 2020). Throuh Local Partners Acción Honduras, ADASBA and CASM, Honduras CO continue the execution of the subsistence and hygiene support component (Result 1) or our Response Plan by delivering Cash transfers to a total of 624  families (3,222 persons), Vouchers to 802 families (3,686 persons) and food baskets to 1,351 families (6,096 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments (Total: 2,777 families, 13,004 persons, $ 76,652.84).

| Cash and Voucher: |  |
| --- | --- |
| Total Families | (US$) |
| 1426 | $ 47,859.35 |

Source:  SIMA Platform, September 10, 2020,

Comment:  Value includes Cash/Voucher ($36.5853)  and kit hygiene ($3.6585):  Total unit: $40.24385.

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism (i.e. mobile money, banking system other financial service provider etc, |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 2,777 | 13,004 | 6,648 | 6,356 | $ 81,869.91 | Cash transfer and in kind |
| Detail |  |  |  |  |  |
| 624 | 3,222 | 1,666 | 1,556 | $ 25,112.20 | Cash (with hygiene kit) |
| 802 | 3,686 | 1,855 | 1,831 | $ 22,747.15 | Voucher (with hygiene kit) |
| 1,351 (*) | 6,096 | 3,127 | 2,969 | $ 34,010.56 | Food Basket and hygiene kit |

(*) Of a total of 1,351 families, 1,046 received a food basket for the second time and 305 families for the first time.

*Source:  SIMA Platform, September 10, 2020

In July the International Office raise an NSP from P&G to prioritize 664 families who are experiencing problems of accessing basic food and hygiene kit in the departments of Francisco Morazán and Santa Bárbara using these three mechanisms: Cash transfer, voucher or food basket.

CVA  executed (August 1 –31, 2020). Through  Local Partners, CO continue the execution of the subsistence and hygiene support component (Result 2) of our Response Plan by delivering Cash transfers and voucher to 472 families (2,430 persons) and food baskets to 1,717 families (7,986 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments (Total:  2,189 families, 10,416 persons, $  68,311.33).

| Cash and Voucher only |  |
| --- | --- |
| Total Families | (US$) |
| 472 | $ 17,268.29 only cash and voucher |

Sources:  SIMA Platform, September 10, 2020; M&E CVA Country Office.

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism (i.e. mobile money, banking system other financial service provider etc, |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 2,189 | 10,416 | 5,260 | 5,156 | $ 68,311.33 |  |
| Detail |  |  |  |  |  |
| 279 | 1427 | 692 | 735 | $ 11,228.05 | Cash (with in kind hygiene kit) |
| 193 | 1,003 | 457 | 546 | $ 7,767.07 | Voucher (with in kind hygiene kit) |
| 1,717 (*) | 7,986 | 4,111 | 3,875 | $ 49,316.20 | Food Basket and hygiene kit |

*Source:  SIMA Platform, September 10, 2020

(*) Of a total of 1,717 families, 1,031 received a food basket for the second time and 686 families for the first time.

ACUMULATIVE APRIL TO AUGUST 2020

Only Cash and Voucher (without in kind hygiene kits)

| Honduras | Families |  |  | US $ |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Previous | News | Total | Previous | News | Total |
|  | 3603 | 472 | 4075 | $122,288.62 | $17,268.29 | $139,556.91 |

All mechanism

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 14,077 | 66,317 | 33,576 | 32,741 | $ 435,914.91 |  |
| Detail |  |  |  |  |  |
| 1,552 | 7,848 | 4,092 | 3,756 | $ 61,251.22 | Cash and hygiene kit in kind |
| 2,523 | 12,459 | 6,097 | 6,362 | $ 93,214.23 | Voucher and hygiene kit in kind |
| 10,002 (*) | 46,010 | 23,387 | 22,623 | $ 281,449.46 | Food Basket and hygiene kit |

(*) Of a total of 10,002 families, 2,077 received a food basket for the second time and 7,925 families for the first time.

Detail information:  Cash and voucher mechanism

| Total Families |  | Total (US$) | Unit cost |
| --- | --- | --- | --- |
| Only cash and voucher (without in kind hygiene kit) |  | $139,556.91 |  |
| 3,489 |  | $ 127,646.34 | $36.5853 each |
| 586 |  | $11,910.57 | $20.3252 each |
| Total Families only In kind Hygiene Kit | Total (US$) |  | Unit cost |
| 4,075 | $14,908.54 |  | $3.6585 each |
| Total Cash and Voucher with in kind hygiene kits: April to August 2020. Total Families; Total (US$). 4,075; $ 154,465.45 (*). |

CVA executed (September 1 –30, 2020). Through Local Partners, CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Cash transfers and voucher to 1,322 families (5,874 persons) and food baskets to 1,400 families (6,129 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments: Total $69,548.

| September 2020: Cash and Voucher only |  |  |
| --- | --- | --- |
| Total families | # families first CVA | # families second CVA |
| 1,322 | 401 | 921 |
| $ 33,390.24 | $ 14,670.73 | $ 18,719.51 |

| ACUMULATIVE APRIL 2020 TO SEPTEMBER 2020 (only families first CVA) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Honduras | Families first CVA |  |  | US $ |  |  |
|  | Previous | News | Total | Previous | News | Total |
|  | 4,075 | 401 | 4,476 | $139,556.91 | $14,670.73 | $ 154,227.64 |

| ACUMULATIVE APRIL 2020 TO SEPTEMBER 2020 (families first and second CVA) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Honduras | Families First and second CVA |  |  | US $ |  |  |
|  | Previous | News and | Total | Previous | News | Total |
|  | 4,075 | 1,322 | 5,397 | $139,556.91 | $33,390.24 | $ 172,947.15 |
| **Sources: SIMA Platform, October 06 , 2020; M&E CVA Country Office. *Only Cash and Voucher (without in kind hygiene kits) |  |  |  |  |  |  |  |

| September 2020: Total families and Mecanisms |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Beneficiaries |  |  |  | Amount transferred (US$) | Amount transferred (Lps.) | Transfer mechanism | % |
| Total families | Total persons | Gender (if available) |  |  |  |  |  |
|  |  | Female | Male |  |  |  |  |
| 2,722 | 12,003 | 6,172 | 5,831 | $69,548.00 | L1,710,880.70 |  |  |
| Detail |  |  |  |  |  |  |  |
| 675 (1) | 3314 | 1721 | 1593 | $18,922.76 | L465,500.00 | Cash transfer | 27% |
| 647 (2) | 2560 | 1282 | 1278 | $16,658.94 | L409,810.00 | Voucher integral support | 24% |
| 1,400 (3) | 6129 | 3169 | 2960 | $33,966.29 | L835,570.70 | Food Basket integral support | 49% |

*Source:  SIMA Platform, October 06, 2020

- Of 675 families that received Cash transfer, 275 correspond to a first delivery and 400 families to a second delivery.

- Of 647 families that received Voucher, 126 correspond to a first delivery and 521 families to a second delivery.

- Of 1,400 families that received Food Basket, 307 correspond to a first delivery and 1,093 families to a second delivery.

Acumulative April – Septiembre 2020   / All mechanisms

| Beneficiaries | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- |

| Total families | Total persons | Gender (if available) |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Female | Male |  |  |
| 16,799 | 76,914 | 39,039 | 37,875 | $ 505,462.91 |  |
| Detail |  |  |  |  |  |
| 2,197 (1) | 11,162 | 5,813 | 5,349 | $ 80,173.98 | Cash and hygiene kit in kind |
| 3,200 (2) | 15,019 | 7,379 | 7,640 | $ 109,873.17 | Voucher and hygiene kit in kind |
| 11,402 (3) | 50,733 | 25,847 | 24,886 | $ 315,415.75 | Food Basket and hygiene kit |

- Of 2,197 families that received Cash Transfer, 1152 correspond to a first delivery and 400 families to a second delivery.

- Of 3,200 families that received Vauchers, 2,202 correspond to a first delivery and 521 families to a second delivery.

- Of 11,402 families that received Food Basket, 6,832 correspond to a first delivery and 3,170 families to a second delivery

- TOTAL:  4,091 families (32%) support second delivery. 100% families with enrolled children support with at least one delivery)

CVA executed (October 1 –31, 2020). Through Local Partners, CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Cash transfers and voucher to 1,113 families (5,235 persons) and food baskets to 2,135 families (9,259 persons) with enrolled children from Francisco Morazán and Santa Bárbara Departments: Total $69,233.59.

| October 2020: Cash and Voucher only |  |  |
| --- | --- | --- |
| Total families | # families first CVA | # families second CVA |
| 1,113 | 203 | 910 |
| $ 25,922.76 | $ 7,426.83 | $ 18,495.93 |

| ACUMULATIVE APRIL 2020 TO OCTOBER 2020 (only families first CVA) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Honduras | Families first CVA |  |  | US $ |  |  |
|  | Previous | News | Total | Previous | News | Total |
|  | 4,476 | 203 | 4,679 | $154,227.64 | $ 7,426.83 | $ 161,654.47 |

| ACUMULATIVE APRIL 2020 TO OCTOBER 2020 (families first and second CVA) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Honduras | Families First and second CVA |  |  | US $ |  |  |
|  | Previous | New | Total | Previous | New | Total |
| First | 4,476 | 203 | 4,679 | $ 154,227.64 | $ 7,426.83 | $ 161,654.47 |
| Second | 921 | 910 | 1,831 | $ 18,719.51 | $ 18,495.93 | $ 37,215.44 |
| Total | 5,397 | 1,113 | 6,510 | $ 172,947.15 | $ 25,922.76 | $ 198,869.91 |

***Source:  SIMA Platform, November 10, 2020; M&E CVA Country Office.

*Only Cash and Voucher (without in kind hygiene kits)

| October 2020: Total families and Mecanisms |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Beneficiaries |  |  |  | Amount transferred (US$) | Amount transferred (Lps.) | Transfer mechanism | % |
| Total families | Total persons | Gender (if available) |  |  |  |  |  |
|  |  | Female | Male |  |  |  |  |
| 3,248 | 14,494 | 7,399 | 7,095 | $69,233.59 | L1,703,146.27 |  |  |
| Detail |  |  |  |  |  |  |  |
| 770 (1) | 3736 | 1908 | 1828 | $19,335.37 | L475,650.00 | Cash transfer | 28% |
| 343 (2) | 1499 | 737 | 762 | $7,330.08 | L180,320.00 | Voucher integral support | 11% |
| 2,135 (3) | 9259 | 4754 | 4505 | $42,568.14 | L1,047,176.27 | In kind integral support | 61% |

*Source:  SIMA Platform, November 10, 2020

- Of 770 families that received Cash transfer, 185 correspond to a first delivery and 585 families to a second delivery.

- Of 343 families that received Voucher, 18 correspond to a first delivery and 325 families to a second delivery.

- Of 2,135 families that received Food Basket, correspond to a second delivery

Acumulative April – October 2020   / All mechanisms

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 20,047 | 91,408 | 46,438 | 44,970 | $ 574,696.49 |  |
| Detail |  |  |  |  |  |
| 2967 (4) | 14898 | 7721 | 7177 | $ 99,509.35 | Cash and hygiene kit in kind |
| 3543 (5) | 16518 | 8116 | 8402 | $ 117,203.25 | Voucher and hygiene kit in kind |
| 13537 (6) | 59992 | 30601 | 29391 | $ 357,983.89 | Food Basket and hygiene kit |

- Of 2,967 families that received Cash Transfer, 1,989 correspond to a first delivery and 985 families to a second delivery.

- Of 3,543 families that received Vauchers, 2,697correspond to a first delivery and 846 families to a second delivery.

- Of 13,537 families that received Food Basket, 8,232 correspond to a first delivery and 5,305 families to a second delivery

- TOTAL:  7,136 families (55%) support second delivery. 100% families with enrolled children support with at least one delivery: 12,911 families).

Other initiatives.

| Beneficiaries |  |  |  | Amount transferred (US$) | Amount transferred (Lps.) | Initiative |
| --- | --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |  |
|  |  | Female | Male |  |  |  |
| 224 | 1120 | 616 | 504 | $3,740.16 | L.92,008.00 | Implementation of traditional family gardens in the municipalities of Santa Bárbara. Joint iniative: ChildFund support with seeds and plants (fruit and medicinal trees) and UE/EUROSAN and Mancomunidad with fertilizers, suppliers, tools and technical assistance. |

CVA executed (November 1 –30, 2020). Through Local Partners, CO continue the execution of the subsistence and hygiene support component (Result 1) of our Response Plan by delivering Cash transfers and voucher to 509 families (2,315 persons) with enrolled children from Francisco Morazán and: Total $ 10,345.53.

November 2020: Cash and Voucher only

Total families

509

$ 10,345.53

| ACUMULATIVE APRIL 2020 TO NOVEMBER 2020 (only families first CVA) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Honduras | Families first CVA |  |  | US $ |  |  |
|  | Previous | News | Total | Previous | News | Total |
|  | 4,679 | 0 | 4,679 | $ 161,654.47 | $ 0 | $ 161,654.47 |

| ACUMULATIVE APRIL 2020 TO NOVEMBER 2020 (families first and second CVA) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Honduras | Families First and second CVA |  |  | US $ |  |  |
|  | Previous | New | Total | Previous | New | Total |
| First | 4,679 | 0 | 4,679 | $ 161,654.47 | $ 0 | $ 161,654.47 |
| Second | 1,831 | 509 | 2,340 | $ 37,215.44 | $ 10,345.53 | $ 47,560.97 |
| Total | 6,510 | 509 | 7,019 | $ 198,869.91 | $ 10,345.53 | $ 209,215.44 |

***Source:  SIMA Platform, November 09, 2020; M&E CVA Country Office.

*Only Cash and Voucher (without in kind hygiene kits)

| November 2020: Total families and Mecanisms |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Beneficiaries |  |  |  | Amount transferred (US$) | Amount transferred (Lps.) | Transfer mechanism | % |
| Total families | Total persons | Gender (if available) |  |  |  |  |  |
|  |  | Female | Male |  |  |  |  |
| 1,058 | 4,565 | 2,375 | 2,190 | $ 30,922.10 | L760,683.60 |  |  |
| Detail |  |  |  |  |  |  |  |
| 212 (1) | 1008 | 530 | 478 | $ 4,308.94 | L106,000.00 | Cash transfer | 42% |
| 297 (2) | 1,307 | 670 | 637 | $ 6,036.59 | L148,500.00 | Voucher integral support | 58% |

*Source:  SIMA Platform, November 09, 2020

(1) The 212 families that received means of subsistence through the Cash transfer mechanism correspondence to a second delivery.

(2) The 297 families that received means of subsistence through the Vaucher mechanism correspond to a second installment.

Acumulative April – November 2020   / All mechanisms

| Beneficiaries |  |  |  | Amount transferred (US$) | Transfer mechanism |
| --- | --- | --- | --- | --- | --- |
| Total families | Total persons | Gender (if available) |  |  |  |
|  |  | Female | Male |  |  |
| 21,105 | 95,973 | 48,813 | 47,160 | $ 605,618.59 |  |
| Detail |  |  |  |  |  |
| 3,179 (3) | 15,906 | 8,251 | 7,655 | $ 103,818.29 | Cash and hygiene kit in kind |
| 3,840 (4) | 17,825 | 8,786 | 9,039 | $ 123,239.84 | Voucher and hygiene kit in kind |
| 13,537 (5) | 59992 | 30601 | 29391 | $ 357,983.89 | Food Basket and hygiene kit |

(3) Of 3,179 families that received Cash Transfer, 1,989 correspond to a first delivery and 1190 families to a second delivery.

(4) Of 3,840 families that received Vauchers, 2,697correspond to a first delivery and 1,143 families to a second delivery.

(5) Of 13,537 families that received Food Basket, 8,232 correspond to a first delivery and 5,305 families to a second delivery

TOTAL:  7,136 families (55%) support second delivery. 100% families with enrolled children support with at least one delivery: 12,911 families).

3.b.2.2.  Bags of food for families

The 30 of April we sign the new grant entitled “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood " with an amount of $752,442, in which for the coming months we will support vulnerable families with children under 6 years old in the departments of Santa Bárbara, La Paz, Intibuca, Lempira, Ocotepeque, Copán affected by the emergency with a bag of food for children between the ages of 2-6 years. We will deliver 5,758 bags consisting of cereal and milk for children that have low weight and are in AIN-C Program.

On June 9 we sign a new workplan with UNICEF  to the ongoing grant “Strengthening the methodology for the progressive eradication of physical punishment” (Job Code 3-0380D)  which consisted of redirecting all remaining activities and the amount of $91,678 to the COVID 19 Pandemia Emergency Response in which consists of 1,517 families with children under 6 years old of Santa Bárbara and Copán Departments  supported in their access to subsistence products to ensure their nutrition.

This week we were able to deliver 360 Food Basket to families with children under 6 years old in the department of Santa Barbara to the  project “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood ".

ChildFund’s Global Response Plan

We are supporting community-based child protection systems that identify, respond to and refer cases of abuse, neglect, violence or exploitation. We are also providing virtual, online psychological first aid and counseling, and supporting temporary shelters for children who live on the street, providing hygiene supplies, food and other basics. We are also arranging safe and appropriate care for children who are separated from their caregivers due to treatment or prevention measures.

ChildFund’s Global Response Plan

We are supporting community-based child protection systems that identify, respond to and refer cases of abuse, neglect, violence or exploitation. We are also providing virtual, online psychological first aid and counseling, and supporting temporary shelters for children who live on the street, providing hygiene supplies, food and other basics. We are also arranging safe and appropriate care for children who are separated from their caregivers due to treatment or prevention measures.

3.b.3. Keep children safe from Violence: physically and emotionally

The development of the response of the emergency plan that is was made between Honduras and Guatemala was completed, this plan completes actions for the implementation of cash transfer and communication actions focusing messages to maintain measures to prevent contagion and protect violence against children, young people and adolescents. Enhancing messages that will instruct and guide mothers and caregivers in the important work of protecting CYA. Messages have also been defined with the context of communities in mind, the current situation of the crisis and specific products have been specialized for young people and adolescents with whom self-care must be worked on to reduce the risk of contagion.

The communication plan will be executed on social media, wsp, print media and radio. In ChildFund's action communities in Honduras, radio remains the most widely disseminated medium and accessed by our target population. Thanks to this plan, both the beneficiary families and the communities where we have actions will be reached.

In progress of this plan, a letter of message was already developed to mothers, fathers, caregivers because it is of great interest and fundamental that even in times of crisis and emergency continue to care for and protect CYA.

We have developed a booklet for mothers, fathers and caregivers, and inside its content it can be found very important messages to take care of children’s health, and to take other measures at home for the security of children inside their home during quarantine. This booklet was printed and it´s being delivered since april 27 in the most vulnerable alongside with subsistence support. It will be used by parents, since in these moments of emergency it requires not to forget about CAY in all their pursuits and concerns. This material is easy to read, with illustrations, short phrases, adapted language to the region and with necessary information.

We have provided guidance to the local partners to elaborate brochures that will help to educate on what violence is, types and signs of violence. These brochures are being delivered to the families in all the communities.

A roadmap for referral of cases of violation was prepared. This roadmap will be used by the community and the community protection mechanisms.

Members of the 17 Community mechanisms of protection, local partners, and the technical team have been involved in activities of distribution of personal hygiene, personal care and livelihood kits. They have been performing the following activities.

- Call for families benefited.

- Application of antibacterial gel.

- Order families and take a distance of 1.5 meters between each of them.

- Distribution of information as a protection measure against COVID 19

Municipal protection councils have guidelines for developing resilience actions and encouraging them to activate the local economy through the local economic development unit of the municipalities.

On May 18, UNICEF requested ChildFund to make changes to the ongoing grant “Strengthening the methodology for the progressive eradication of physical punishment” (Job Code 3-0380D) in which consisted of redirecting all activities and remaining amount of $91,678  to new activities  being one of them: 2. Delivering a booklet (4 sides) to 1,500 families in the department of Santa Bárbara and Copan containing key messages related to the contents covered by the Methodology, and follow-up cellular phone  text messages. These materials will be developed and designed by the UNICEF and ChildFund International technical team.

On June 09 we sign a new workplan with UNICEF  to the ongoing grant “Strengthening the methodology for the progressive eradication of physical punishment” (Job Code 3-0380D)  which consisted of redirecting all remaining activities and the amount of $91,678  to the COVID 19 Pandemia Emergency Response in which consist of delivering a booklet (4 sides) to 1,517 families in the departments of Santa Bárbara and Copan containing key messages related to the contents covered by the Methodology for the progressive eradication of physical punishment, and follow-up cellular phone text messages. These materials will be developed and designed by the UNICEF and ChildFund International technical team.

The community protection mechanisms continue to actively supporting the giving of cash,  vouhers, grocery and  hygiene kits, ensuring and  verifying that each beneficiary keeps the biosecurity orders and measures.

Developing the topics of children rights infringement with community leaders  and monitoring the action plan of the communities  through the use of virtual platforms, strengthening the  knowledge of Community  Protection Measures during the COVID-10 emergency.

During the month of August virtual sessions have been carried out in order to strengthen CBCPM where the needs that prevent abuse, negligence, exploitation and violence were analyzed and prioritized, letting them know the derivation route for cases of rights infringement  with the tracing report format articulated with municipal councils, DINAF and justice operators.

Municipal councils of rights guaranteeing participated in the conference on rights infringement through the Childhood Code and promotion of the derivation route of cases and its linkage to the justice operators and DINAF.

Activities were carried out through the different social networks to send key messages addressed to caretakers and families on how to deal with the stress, child protection, with messages that contribute to the prevention, protection and self-care of teenagers and young adults and infographics on: how to keep a good emotional health, how to help our children to express their emotions on how child abuse is manifested.

Example of the local partner CASM of messages and infographics

https://drive.google.com/file/d/1ap1miMA36dyKn5vOyAvFiYR4P1Aibclw/view?usp=sharing

I

ChildFund’s Global Response Plan

While schools remain closed, we are supporting children’s learning through activities and tutoring sessions online or by radio. For students without reliable internet access, we are distributing home learning kits with materials and guides for their use.

ChildFund’s Global Response Plan

While schools remain closed, we are supporting children’s learning through activities and tutoring sessions online or by radio. For students without reliable internet access, we are distributing home learning kits with materials and guides for their use.

3.b.4. Help children continue to do their job: Learning

The 30 of April we sign the new grant entitled “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood " with an amount of $752,442, in which for the coming months we will support vulnerable families with children under 6 years old in the departments of Santa Bárbara, La Paz, Intibuca, Lempira, Ocotepeque, Copán. Children under the age of 6 their development could be affected by the emergency crisis of covid-19 for this reason is important to continue actions for the integral development of children particularly on children with disability, neurological risk and/or development below the curve. As an  emergency response we will deliver them 3,000 early stimulation sets with their respective booklet for they can continue their learning.

On June 16 we sent a proposal to TIGO entitled “Learning and entrepreneurship with the cybermobile” with the objective to support our youth in developing technological skills for entrepreneurship and digital self-learning through the pandemic crisis.

On  July 31st we presented a proposal to Tinker Foundation entitled “Support for children from urban and rural communities in Honduras with virtual tutorials including a focus on protection to improve learning in Mathematics and Spanish during the COVID-19 Pandemic” the main objective is to “Strengthen essential competencies in Mathematics and Spanish for children with a strong probability of grade failure using alternative means to formal education and help prevent different forms of violence which may occur in the home”. We are planning to reach 3,000 children for the urban and rural communities from the departments of Francisco Morazán, Cortés and Santa Bárbara.

3.b.5. Other responses

The 30 of April we sign the new grant entitled “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood " with an amount of $752,442, in which for the coming months we will support pregnant women and newborns in the departments of Santa Bárbara, La Paz, Intibucá, Lempira, Ocotepeque, Copán with a diaper bag. We will deliver 2,716 diaper bags containing necessary supplies for a proper health care to newborns under this emergency.

Below Sections for Internal Use Only

Part 4: Office and Staff Status

| Office Status (Open/Closed) | Number of Staff: OP 14; GSS: 3; Descentralizado Proyect: 19; Prevención de la Violencia UNICEF Proyect: 2; CONFIO Proyect: 6; P&G Proyect :1; Criando con amor Proyect: 37; RISP: 78 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Diagnosed with COVID19 | Diseased from COVID19 | Working from Office | Working from Home | On Special Leave |
| Closed | 3 | 0 | 0 | 29 | 0 |

*others may be combining work from home and on the field due to Grants

On September and October new collaborators entered the new project RISP, financed with BID funds.

Notes:

- Any cases of staff diseased need to be reported immediately to RD and GHR.

- Special leave as per COVID19 Administrative Guidelines.

Number of staff/partner organization staff completed WHO COVID online training https://www.who.int/emergencies/diseases/novel-coronavirus-2019/training/online-training.

Honduras staff training

- Leadership in times of change

- La Comunicación en tiempos de coronavirus. Universidad Andina Simón Bolivar

- Tendencias post pandemia en el mundo de las ONG

- Aceleración de la transformación digital en el contexto de coronavirus

- Periodismo de soluciones en tiempos de pandemia

Part 5 Human Resources

- Which visitors are there in the country ? 0.

- Please include names, functions, contact information and arrival/departure dates for both IO and RO staff (note: due to the travel ban, this will apply only once the ban has been lifted)

- Any gaps in staffing/need for deployment from other COs or Global Teams?

- Are there any other major HR issues?

Meeting with all staff:

Advances and challenges

Working from home

Scenarios before COVID 19 and security measures – UN

May 25

Review Information on Biosecurity measures

Jun 1

Preparation of biosafety protocol

June 10

Preparation of documents for Bio security Training (Return to the office)

June 17

Personal training of projects in biosecurity measures (June 12)

- CONFIO project

- "Criando con Amor" Project

June 22

Biosafety document completion

Security Committee Information

Relatives of two ChildFund staff has been affected by COVID-19.  They are in strict quarantine and under medical treatment.

Relatives of 3 staff members has been affected by the Coronavirus. The mother of one staff has passed away due to the Coronavirus. HR is in contact with the staff affected in order to provide any kind of support.

One staff of the Primary Health project is under observation due to has been in contact with people affected with the Coronavirus.  .

Virtual training has been conducted to all staff in biosecurity measures on June 26

This week we delivered 32 hygiene kits (antibacterial gel, masks and gloves) to the personnel of the project “Support to the implementation of the work plan of the Strategy Criando con Amor with emphasis on Covid-19 for early childhood ".

Biosafety protocoles trainings will be held on November for all staff CO.

Part 6 Safety & Security

- Are police and other services functioning in the normal manner?

Yes.

- Are the courts still operating?

No, they are suspended until  March 30, 2020. Partially functioning

- Are there reports of looting or increased criminality?

No.

In Tegucigalpa people has reported robberies and manifestations against the government.

- Have military personal being deployed to patrol towns or cities?

Military and Police are patrolling during the curfew.

- Confirm the safety of staff and their families in the affected area.

The staff is safe.

- Have Safety and security risks/mitigation plans been updated to current environment?

No, still pending.

- Recommendations around any upcoming travel planned for staff or donors (note: Only once global travel ban has been lifted)

All travel of staff and donors are suspended

Part 7 Grants

List all active grants:

| Grant Job Code | Grant Name | Donor | Status of Implementation (Normal/Reduced/Suspended) | Any specific guidance received from donor? (Yes/No) |
| --- | --- | --- | --- | --- |
| 2-0358D | Provision of Primary Health Care | Ministry of Health | Normal | Yes, Emergency Response Guideline to COVID-19 |
| 3-0380D | Strengthening the Methodology for the progressive eradication | UNICEF | Reduced | Yes Redirect activities due the emergency |
| 25-053D | Safe Water for Children in Honduras | P&G | Reduced | No |
| 12-0354D | CONFIO | Global Affairs Canada | Reduced | No |
| 2-0371D | Support in the Implementation of the Strategy "Criando con Amor" with emphasis on Covid-19 | SEDIS(GOH) | Normal | No |
| 2-0371D/2-0373D/2-0372D | Immediate Public Health Response Program to Contain and Control Covid-19 and mitigate its effect on service delivery in Honduras (RISP-HO) | Ministry of Health | Normal | No |

Provide any additional narrative on how the COVID19 crisis affects implementation of your major grants.

  - Strengthening the Methodology for the progressive eradication-UNICEF (3-0380D): UNICEF requested us to redirect activities in the ongoing grant to support 1,500 families with complimentary livelihoods and a booklet about the Methodology for the progressive eradication of physical punishment, which will be monitor by cellular phone text messages.

  - Safe Water for Children in Honduras-P&G (25-053D): This week 144,000 Sachets were distributed to support the health center the rest of the activities in the field reduced due to the quarantine.

  - CONFIO-Global Affairs Canada: All staff are working with Regional Project Team and Country Office team in identifying alternative ways to implement activities to achieve indicators.

  - Support in the Implementation of the Strategy "Criando con Amor" with emphasis on Covid-19: We will delivering bags of food, hygiene kits and early stimulation sets.

  - In the framework of the Convention No. 116-SEDIS-2020 of cooperation and technical assistance between the Ministry of social development and  inclusion and ChildFund for “Support to the Criando  con  Amor strategy, prevention and response to the COVID-19 emergency for early childhood, benefitting with a donation of grocery kits during the months of June and July to 625 families  with children under 6 years in the department of Santa  Barbara with a value of L.603,250.00 as counterpart for family investment.

  - In relation to the governmental  Project "Criando con Amor" (Raising with Love) a series of activities had  been carried out  to support children´s development one of them domiciliary visits:  A total of 11,714 families have been visited , orienting and training them in the care and attention that their children need, promoting changes of behavior in the parenting patterns using guides for the formation of the families (Catrachitos guides)

    - Activities carried out by the program Criando con Amor during the month of September

    - 6,051 families identified and incorporated with processes of training in Early Childhood Development and 3,497 children with Childhood Development monitoring.

    - 4,660 hygiene kits distributed to prevent prevalent diseases and COVID-19 in Early Childhood, with the delivery, Catrachitos guides were attached for new families, giving them advice in the use of the hygiene kit and Early Stimulation.

    - Purchase and distribution to the departamental health regions of 5,758 bags of fortified cereal and milk for the nutritional support to vulnerable families with children in the ages of 2-6 years with under weight.

    - 31 religious leaders trained in childhood development care,

    - 1,134 municipal commissions working in monitoring and workplans.

First Lady in Santa Bárbara

During the emergency of hurricane ETA, in humanitarian response, the Criando con amor project has supported shelters in Tegucigalpa and the north coast with the delivery of: 135 hygiene kits for children under six years of age, 20 diaper bags, 495 milk cans, 195 disposable diapers at a cost of $6,000.00.

Part 8 Funding

Provide information about potential sources of funding, including grant donors, subsidy, Emergency Action Fund, Alliance members, GIK, etc., for these emergency response efforts using the chart below:

| Donor | Program | Amount (USD) | Requested? (Y/N) | Confirmed? (Y/N) |
| --- | --- | --- | --- | --- |
| Lutheran World Relief | GIK | USD.6,360 | Y | Y |
| Lutheran World Relief | GIK | USD.32,038.5 | Y | Y |
| P&G | GIK | USD.5,040 | Y | Y |
| P&G | GIK | USD 6,401 | Y | Y |
| LOTO | GIK | USD 1,000 | Y | N |
| SEDIS GOH (Criando con Amor) | Grant Donors | USD 1,000,081 | Y | Y |
| UNICEF | Grant Donors | USD 91,678.63 | Y | Y |
| ChildFund International | Subsidy Funds | USD.83,074 | Y | Y |
| Local Grants* | COVID-19 appeal | USD 91,580.4 | N | N |
| Local corporate donors (cash or in kind) * | COVID-19 appeal | USD 91,580 | N | N |
| Corporates IO | COVID-19 appeal | USD 122,107.2 | N | N |
| Canadian Embassy in Costa Rica, Honduras, Nicaragua | Grant Donors | USD 30,055 | Y | N |
| ChildFund International Office | EAF | USD 25,000 | Y | Y |
| TIGO | GIK | USD 4,598 | Y | N |
| Tinker Foundation | Grant Donors | USD 75,000 | Y | N |
| Ministry of Health (GoH) | Grant Donors | USD 611,287 | Y | Y |
| P&G | NSP | USD 26,872 | Y | Y |
| P&G | Grant Donors | USD 75,665 | Y | Y |
| Lutheran World Relief | GIK | USD 13,100 | Y | Y |

- Budget

  - Outline how we will use this funding with a rough topline budget.

  - Potential subsidy funds (25% March & April) are planned to be expensed in either emergency/sanitation kits and/or cash transfers to sponsored families in need.

Proposed actions will come from Local Partners.

  - As the response to the Covid-19 the Secretary of Development and inclusion (SEDIS) required ChildFund  to make changes in the programmed activities to the new proposal “Integral Care System for Early Childhood “Criando con Amor” for the coming months  April, May, and June e to support vulnerable families affected by the emergency. This emergency response consists of the following:

    - 7,000 hygiene kits for families with children under 6 years old.

    - 3,000 early stimulation sets for boys and girls with disabilities under 6 years of age.

    - 3,000 bags of food support to vulnerable families with children between the ages 2-6 years that have low weight who are in AIN-C Program (Cereal and milk).

    - 1,500 USBs for Community Media to send messages to the community in how to prevent the virus COVID-19.

  - We presented a proposal to the Canadian Fund Local Initiative of Honduras, Costa Rica, Nicaragua which consisted of the following (Not approved):

    - At least 80% of patients with chronic diseases receive timely medical treatment. (29% men and 71% women)

    - 29 health centres equipped with personal protection supplies in the municipalities of Curaren, Alubaren, Reitoca, La Venta and Lepaterique in the department of Francisco Morazán.

    - 29 community health centres have educational materials and support instruments to implement a communication plan on protection, prevention and self-care measures and what to do in the event of suspected symptoms or signs of COVID-19

  - On July 31st, we presented a proposal to Tinker Foundation with the general objective  that Children with a strong probability of grade failure improve essential competencies in Mathematics and Spanish, and learn about prevention of violence, using alternative means to formal education during the COVID-19 pandemic. We are expecting the following results:

    - 3,000 children and adolescents who are tutors and students in the Departments of Francisco Morazán, Santa Bárbara and Cortés improve learning in Mathematics and Spanish.

    - 3,000 children and adolescents can identify and protect themselves from different forms of violence.

    - 113 teachers have strengthened competencies in information and communication technology (ICT) are able to use the virtual platform.

    - Parents encourage their children to read using educational material on prevention of violence.

  - The 10 of September we signed agreement with the Ministry of for the project “Health  Immediate Public Health Response Program to Contain and Control Covid-19 and mitigate its effect on service delivery in Honduras (RISP-HO)”. The project contribute to the strengthening of the First Level of Care networks, facilitating timely attention to the population through support for strategic and operational epidemiological surveillance actions for preventing the spread of the disease, containing transmission, improving access and care of suspected and positive cases of COVID-19 in Honduras.

  - The 15 of October we signed an agreement for the IV phase for the project “Clean Water for Honduras” with emphasis in Covid-19 prevention, this phase will have components such as multiple aspects geared towards COVID-19 prevention (clean water, hand washing stations for schools and health clinics, biosecurity kits for volunteers, Covid-19 prevention campaign, additional sachets with other nonprofit organizations, etc.)

  - In November Lutheran world relief approved a second round of assistance in this case will be oriented to support the triple emergency of Eta, IOTA and Covid-19. The support directly targeted to Covid-19 consists of 13,100 cloth masks that will be distributed in the municipalities of Alubaren, Curaren, Lepaterique and Reitoca.

Part 9 Media/Communications

  - List of media who will be or have been contacted with press releases.

- The information in response to the emergency alongside photographs from donations and other actions will be sent via social media such as Facebook, Twitter, and Instagram. With educational and child protection messages.

  - List of emergency CO spokespeople, including name, location, contact information, and languages spoken.

Rodrigo Bustos, Country Director, rbustos@childfund.org, 502 40161393

Waleska Zelaya, Advocacy and Communication Specialist, zzelaya@childfund.org, 504 99317903

Spanish, English.

  - Plans for collecting photos/videos/stories, e.g., should an outside photographer be hired?

- Photographs from the actions and donations are captured by the focal points of communication and technicians who are inside the communities. By this moment, we have donated 2,000 hygiene kits for people at a high risk to contract the COVID19 in the south of Francisco Morazán, which will be distributed through health centers in the city. Water purification sachets have also been donated. The Photographs will be attached.

- It has also been made known about the donations of hygiene kits to DINAF

- It has also been made known about the donations of food, booklets and hygiene kits for people and SINAGER.

- It has also been made known about the donations of food and hygiene kits for people in different locations.

- It has also been made known about social media fund raising campaign by Covid-19.

- It has also been made known about the donations of food, booklets and hygiene kits for people.

- Children have made beautiful pictures a poetry and we share this in social media.

- It has also been made known about the donations of food, booklets and hygiene kits for people.

- It has also been made known about the donations of food, booklets, hygiene kits for people and thanks to sponsors.

- Communication messages has been produced to show food donations, booklets and hygiene kits for people, artistic expression for children, protection messages and a fund raising campaign by Covid-19.

- 6 new radio theaters are published in 6 different radios, which their topics are: protection, gender, referral routes, safety measures, etc.

- ChildFund Honduras website is ready to strengthen ChildFund image and local fundraising campaign.

- The video of the Virtual Forum on the impact of Covid 19 on unemployment as a cause of irregular migration, made by the CONFIO project, has been published. Videos on hand washing and radio theaters, among others.

- The launch event for the ChildFund Honduras fundraising webpage and portal was held.

The event was held virtually, with the participation of lawyer Lolis María Salas, director of the Child and Family Directorate, Dr. Elmer Villeda, director of KNH, Elena Quiroz from Social Responsibility Fundation and Patricia Hernández from Bank Credomatic as invited guests; also, with the assistance of representatives from organizations that works for children, private companies, the press and influencers.

A tour was made of the fundraising page and portal, where each donor can choose between the suggested amounts or place an amount of their choice, it must also indicate if it is a one-time donation or a recurring donation.

During the event, an allusion was made to ChildFund's work at the international level, ChildFund in Honduras, the importance of the cause that we promote, the importance of organizations that work for children. The cause for this initiative to raise local funds was explained and the people was invited to donate for supporting a family during this pandemic. As it is necessary to show solidarity with those who live the consequences of Covid-19.

- -Three new radio stations aimed at young people were published, on two radio stations, one regional and one local.

- We designed a booklet for painting, for children, with information on covid prevention.

- We produce a podcast for young people, which is spreading on mobile phones.

-The three radio plays aimed at young people were published again, on two radio stations, one regional and one local.

We made a video to strengthen the work of the protection subcluster, related to how children are affected in their education by covid19.

As part of the work of the protection subcluster, an advocacy and communication team has also been formed in which we are working to improve the conditions of return to school. In addition, together we are deploying an educational campaign aimed at children to improve their habits in the face of covid19.

- A painting notebook for children was designed and will be printing in this quarter, “Recrearte”.

- A campaign for local fundraising has been launched in light boxes through the streets of Tegucigalpa.

- 6 new radioteatre are ready to be recorded, with messages on covid prevention and pandemic care.

  - Key points for messaging and visibility, particularly any host-government sensibilities that must be considered.

- We have prioritized messages for childhood protection in this context, prevention measures, such as washing hands, avoid contact, personality, misinformation, questions, and answers. Also government recommendations, such as staying at home, and following the health measures.

- Support needed or requested from IO, GSS or Global Teams – whether onsite or remote.

We need from P&P particularly from Business Development to consult with Children Believe if there will be time extension of the CONFIO Grants.

Photographs

Delivery of hygiene kits on March 23, 2020, in the south of Francisco Morazán.

Hand washing campaign, Santa Barbara, March 13, before the alert declaration.

Health personnel is trained in the technique of purifying water.

Delivery of more than 10,000 hygiene kits to the Direction of Childhood and Family 17/4/2020

Delivery of hygiene kits to the teams of the National Risk Management System of the municipalities of Santa Bárbara, Atima, San José de Colinas and Trinidad, Santa Bárbara(Department of Santa Bárbara) April 20 and 21, 2020 by the local partner.

Delivery of booklets in Santa Barbara 28/4/2020

Delivery of food supplies to families on insulation in Santa Barbara by the local partner, ADASBA.

Delivery of food supplies to families in Santa Barbara, communities of Corosal, Atima, La Alegria

and Guama.

ChildFund started the delivery of food donations and hygiene kits in Santa Barbara and South of Francisco Morazán, to benefit thousands of people and contribute to the reduction of their vulnerability faced by the consequences caused by Covid-19.

Delivery of food supplies to families in San Vicente Centenario, El Níspero, La Arada, Santa Rita.

Delivery of cash transfer in Lepaterique

Children have made beautiful pictures.

Delivery of food supplies to families in San Vicente Centenario, El Níspero, La Venta, Emituca, San Marcos, in south Francisco Morazán

Child reads the booklets

Post about how to get information to stay healthy

Delivery of food donations

More families are getting food donation

Kenia receives help

My name is Kenia,  I have two kids, Asli, an 8 year old and Manuel, a 5 year old. I feel very glad to receive this food provision, as the other benefited families I want to thank ChildFund, that through CASM has been present during this pandemic, who has affected us a lot.

I am a single mother and I don't have a formal job, I dedicate myself to help my parents in a small Pulpería.

Thank you very much.

Marina receives support

My name is Mariana, I am a single mother. I have three daughters, who are 11, 16 and 19 years old.

During this Covid-19 emergency we have been affected since we are not able to do our daily activities. I dedicate myself to my three daughters, I wash other people's clothes, I do house keeping and make tamales for sale, I haven't been able to make these activities due to Covid-19.

My three daughters do their homework, catching up with school on the internet, they go to a neighbor's house who let's them use the internet.

During this season we have been following the bio-securuty measures such as hand washing and staying home.

We are very greatful with ChlidFund, that through CASM has supported us with this food provision, which will be very helpful in my home, I thank every sponsor because this would not be possible without them.

Mrs. Lourdes

Before the emergence of COVID-19 I was selling tamales, mounds, cupcakes and food. Neighbors were looking for these products here in my house, but now, under this situation, I haven't been able to do it for fear of getting infected and infecting my daughters.

What situation has been the most difficult in this time?

There are several, getting sick and not being able to attend a care center. Between me and my daughter, we cooked medicinal herbs, gradually I was relieved.

We have also had a lot of difficulty with the online education system because you don't always have money to buy a top-up.

There is also no transport for this municipality, nor for the purchase of food.

For all this receiving the provision of #ChildFund, it was of great help, because we did not have many resources to buy the food. I live gratefully to the sponsors and to the people who make this kind of help possible, I know that all the families who received this support are too. Had it not been for food and hygiene materials, our situation would have been worse; one of a mother, she doesn't mind going hungry and struggling, but no one wants to see her daughters suffer, that makes you feel the worst human being on earth.

Moments from the launch event of the website and fundraising portal, attended by the director of the children's and family management, Loly Salas.

Official sponsor of the Central America Donors Forum (CADF 2020), which was held virtually from September 1-3, 2020. The CADF is a highly influential annual event organized by the Seattle International Foundation that unites the international philanthropic community with hundreds of corporate, government, and civil society leaders across Central America. As an official sponsor of the event, ChildFund will enjoy high-level opportunities to offer our significant contributions to the discussions on the 2020 theme of Reinvention & Resistance in Times of Crisis and promote the inclusion of youth leadership and participation. In addition, sponsorship offers us tremendous exposure, brand visibility, and international media coverage. Here’s a snapshot of our engagement t:

- PANEL Session: ChildFund is lead a panel session on Weds, Sept 2nd at 2pm Eastern titled, “Program Delivery for Children & Youth in the Context of COVID-19: Adapting Development Approaches and Leveraging Technology & Partnerships”. The panel was moderated by Mario Lima, and feature two youth champion speakers (including Astrid! –) from Honduras and Guatemala, Rodrigo Bustos, and private sector partners from TIGO Guatemala and the Honduran Foundation of Corporate Social Responsibility (FUNDAHRSE in Spanish)

- Virtual Exhibit: As a sponsor, ChildFund has leveraged the opportunity to demonstrate a united ChildFund Alliance partnership in the region and gain visibility for regional programming

- Participation: From ChildFund, the following colleagues participated live in the three-day Forum: Mario Lima, Rodrigo Bustos, Mike Vargas Corzantes, Allison Iraheta, Josue Rivera, Borys Chinchilla, Amber Stone (consultant), and myself. From our Alliance partners, Ramón Gonzales (CD Guatemala-Educo), Alicia Avila (CD El Salvador-Educo), Maria Isabel Lopez (CD Nicaragua-Children Believe), and Mauricio Castillo (CD Nicaragua-Educo).

September 22, 2020 - ChilFund presented a webinar with the support of FUNDAHRSE to the corporate sector titled “Reinventing the design and implementation of programs for children and youth in the context of COVID-19", we expose ChildFund´s  emergency response with 2 youth speakers, 1 girl  and the local partner Acción Honduras as panelists. We share our experience to 80 participants of different organizations and companies of the private sector in Honduras.

Family receives donation

Reina Alejandra, 11, her 2 brothers and 3 cousins now have food in her home, thanks to #ChildFund's food donation, in a community in Santa Barbara.

Her mother, Reina Isabel, 52, single, has been unable to generate income because her productive activity is the production of petates and in times of pandemic she has not been able to sell anything.

Food was scarce at his table in order to survive. With tears in her eyes, Mrs. Reina told us, "The day the food was given to me, we had nothing to eat, we received this blessing. My sons and nephews were happy because there is now food for several days. I am very grateful to ChildFund and its sponsors for their humanitarian actions in the community, because like me, there are many low-income, jobless families who can't buy beans."

We have a new infographic on ChildFund's response in Honduras

Mupies campaign

Painting notebook for children (some pages)

RecreArte and Children

Protecction Event