**ChildFund International**

**Humanitarian Situation Report Template**

**Humanitarian Situation Report [#24]**

**COVID-19 – [Brazil]**

**[04.09.2021]**

**[Point of Contact – Gabriel Barbosa – Program Manager]**

**[From March 06, 2021 to April 03, 2021]**

**FOR UPDATES, PLEASE HIGHLIGHT UPDATED SECTIONS IN RED**

Part 1: The Overall Situation

COUNTRY

|  |  |  |
| --- | --- | --- |
| Total Number of COVID-19 Cases Reported | Number of Deaths | Number of Cases Recuperated |
| 13,279,657 | 345,025 | 11,732,193(from Ministry of Health) |
| SOURCE : <https://www.arcgis.com/apps/opsdashboard/index.html#/bda7594740fd40299423467b48e9ecf6>  [https ://covid.saude.gov.br/](https://covid.saude.gov.br/) As of April 09th | | |

ChildFund-supported areas (Provide only if you have reliable data on this. You can report on a consolidated basis or by program state/region/province/etc. if you have this detail.)

|  |  |  |  |
| --- | --- | --- | --- |
| Geographical area (country or state/region/province | Total Number of COVID19 Cases Reported | Number of Deaths | Number of Cases Recuperated |
| Minas Gerais | 1,192,050 | 26,795 | Not Available |
| Goiás | 501,814 | 12,518 | Not Available |
| Ceará | 572,618 | 15,059 | Not Available |
| Piauí | 215,140 | 4,379 | Not Available |
| Bahia | 828,466 | 16,232 | Not Available |
| Pernambuco | 364,354 | 12,623 | Not Available |
| SOURCE: National Ministry of Health or other reliable source (<https://covid.saude.gov.br/>) As of March 10th | | | |

* Any relevant background information about areas affected.

The local governments have suspended all the activities except the essential services such as supermarkets, pharmacies. The country is in quarantine.

The Minister of Health was replaced last week and the current one seems to have a less conservative position regarding the recommendations of the World Health Organization and measures taken by the federal government to avoid the spread of the virus. There is no clear position related to the benefits of social isolation. In addition, there is a pressure suffered by the Ministry of Economy from the business market to consider re-opening other segments closed until now.

The Minister of Health resigned from his position last week and a temporary person was appointed to act until a new professional is chosen.

The confirmed cases are increasing rapidly. The governments are taking additional measures, including adopting of in-country “lockdown” in some regions.

In the State of Ceará, where ChildFund Brasil is operating, the number of cases comparing to the country numbers are very high. We’ve received 03 reported cases from enrolled family members living in the communities. One more case was reported of a female youth from the region of Ceará. We are keeping record of the cases reported.

In some regions, local governments are considering the flexibility of opening the local market gradually. The numbers of cases are increasing in the countryside.

In terms of confirmed cases, the numbers are still increasing in the countryside where most of our Local Partners are located. In addition, especially in the city of Belo Horizonte (where our Country Office is located) and in the metropolitan region, the cases are increasing.

Brazil is flagged as the second country in the world in number confirmed cases. The government is also investing in testing the population to anticipate confirmation, especially on cases without symptoms.

Discussions were made around the metrics of the federal government in recording the numbers of confirmed cases, especially on how the national press is giving visibility. Therefore, a pool of media and communication companies was established to support on the data collection and providing accurate information.

According to the global overview of the COVID situation, Brazil’s Federal Supreme Court ruled that the federal government must resume regular publication of the complete data on the evolution of the COVID-19 pandemic in Brazil. The Health Ministry had omitted the number of deaths, for example. In Brazil, pharmaceutical companies and laboratories are laying the groundwork to produce a cheaper and safer COVID-19 test and a vaccine. The announcement is aligned with the approach from Interim Health Minister Eduardo Pazuello, who intends to prioritize medical screening –including temperature and blood pressure checks, as well as medical examinations –oversocial distancing as the country’s top policy to fight the spread of COVID-19. It is uncertain Brazil will be able to implement such an approach, which is drawing criticism, in the immediate future. The acceleration of contagions has threatened efforts to relax quarantines. Responses in Brazil continue to vary internally as local officials struggle to balance economic and sanitary concerns

As per Fundação Cabral Report, with the reopening of the economy in most cities, many wonders whether Brazil can face a second wave of Covid 19. Data show that at least five states have upward curves of daily deaths: Pernambuco, Bahia, Minas Gerais, Mato Grosso and Paraná. São Paulo oscillates, but at a high level. And Goiás begins to show signs of elevation of the curve.

At the same time, there was a significant drop in the occupancy of ICU beds in some states, which is quite significant, since the biggest fear in relation to the coronavirus is the collapse in health. Greater São Paulo, which had peaks of 90% of beds occupied in May, is now 66%. The city of Rio, which reached 93%, is 73%.

In Brazil, since June 3, we have had about a thousand deaths daily. So, we are not in danger of facing a second wave because we have not yet finished the first.

We still have an interim Minister of Health and the government is working on a final decision to appoint a permanent person.

After more than a hundred days of isolation, the scenario creates an environment of false relief and the cities are intended to come back to life. However, we still have limited number of people to avoid agglomeration and restrictions ongoing. Since June 3rd, we record an average of one thousand deaths per day. Different segments of the economy have put pressure on local governments to reopen businesses, however, with the scenario of increasing cases in the interior regions of the country, this decision is very difficult. At country level, the federal government is taking into consideration those aspects in order to re-schedule all the massive initiatives such as ENEM (eg. University entrance exams) to be in place in the coming months.

Our President tested positive for COVID-19 on June 06th. He is in quarantine for the coming days.

In the municipality where our Country Office is based, the city of Belo Horizonte-MG, the mayor decreed lockdown again, due to the increase in the number of cases tested positive.

According to the local press, there is a variation in the situation of reported cases between states and municipalities throughout the country. In regions where the situation previously stabilized, cases have increased. In the regions where ChildFund Brasil operates, among the six states, Minas Gerais and Piaui are on an increasing curve and the others are stable or decreasing.

The federal government continues to delegate decisions to reopen local businesses and schools to local governments. The government is launching digital inclusion programs for high school students so that students have the option to attend classes remotely. It is also evaluating the possibility of expanding the emergency cash assistance that is provided monthly to families.

The number of new cases of Covid-19 has stopped growing in 70% of the 324 Brazilian cities with more than 100,000 inhabitants. Among the states, 12 do not have large municipalities with an accelerated increase in contagion. In 132 of these municipalities (41%), the situation is stable: the number of new diagnoses is constant, but the volume is still significant. Another 95 (29%) are slowing down, with a number of new cases dropping considerably. In the remaining 97 cities (30%), however, the stage is accelerating, that is, the spread of the virus is increasing, with the growth of new cases. Of the 27 capitals, Palmas, Florianópolis, Porto Alegre and Campo Grande are in this situation.

The case and death curves of Covid-19 in Brazil have fallen drastically in the last two weeks, a situation that places the country at a time similar to that of the United States. Since September 14, the trend in the moving average of deaths has remained stable, that is, the number has not presented a significant increase or decrease compared to the previous 14 days. Before that, the country went through a period of one week with a downward trend in the registration of deaths from Covid. In terms of cases, Brazil had a 27% decrease in the period – from 260.6 occurrences to 180.1.

In the regions where ChildFund Brazil operates, among the six states, all are in a situation of stability or decrease in cases. However, local governments are very cautious in deciding on the reopening of businesses and especially schools. Large urban centers are deciding to gradually reopen local commerce according to established protocols in phases. The federal government has already expanded the emergency aid (cash assistance) that is provided monthly to families but with a value reduced by half until December.

Among the 10 states with the highest number of new cases registered, São Paulo, Ceará, Minas Gerais, Goiás, Rio de Janeiro, Rio Grande do Sul and Bahia registered the highest numbers of incidents, respectively. The states of Minas Gerais, Rio Grande do Sul and Goiás showed a reduction compared to the previous period, an increase in Bahia and Ceará and a stabilization in São Paulo and Rio de Janeiro. Regarding the new deaths registered, São Paulo, Rio de Janeiro and Minas Gerais had the highest numbers respectively. Comparing the previous period, there was an increase in Rio de Janeiro and Minas Gerais and a stabilization in São Paulo in the number of new deaths. For the country, the incidence rate until October 10, 2020 was 2,419 cases per 100,000 inhabitants, while the mortality rate was 71.5 deaths per 100,000 inhabitants. There is a forecast that in the coming weeks there will be an increase in the number of cases due to a possible second wave.

In the regions where ChildFund Brazil operates, among the six states, there was a variation with an increase in registered cases in some areas. However, governments continue reopening the commerce, especially schools. Large urban centers are deciding to gradually reopen local commerce according to established protocols.

Brazil has just completed the municipal elections period. It is possible that after the elections, elected officials and other government officials will concentrate on the task of handling a situation that is complicated in health terms and has not yet been resolved in economic terms. The result of the municipal elections should be the beginning of a more acute phase. Transmission rates are on the rise again, according to the latest study published by the Epidemic Control Center at Imperial College London.

The country has an average of 588 deaths from Covid-19 per day, the highest in almost two months, with a total of 178,995registered deaths and 6,728,452Covid-19 diagnoses since the start of the pandemic. The list of states with the most deaths from covid-19 is headed by São Paulo (42,788), Rio de Janeiro (23,017), Minas Gerais (10,227), Ceará (9,683) and Pernambuco (9,119). The Federation Units with the lowest deaths from the disease are Acre (731), Roraima (740), Amapá (823), Tocantins (1,175) and Rondônia (1,589).

Of the seventeen states that showed an increase in the moving average of deaths, ChildFund Brazil operates in two of them – Ceará and Pernambuco. However, the governments continue with the reopening of commerce and few schools, but according to the age of the students. Most of them are with remote classes, over the internet. Large urban centers and local commerce are reopening in accordance with the protocols established in the prevention phases.

Regarding the programmatic response, Childfund Brasil continues to deliver the food & hygiene kits and promote virtual educational and preventive actions with families and children.

The consortium of press vehicles published a new survey of the situation of the coronavirus pandemic in Brazil based on data from state health departments. The country has reached a total of 233,520 deaths since the start of the pandemic. In confirmed cases, since the start of the pandemic 9,599,565 Brazilians have had or have the new coronavirus. In general, there has been na increase in the number of cases where ChildFund Brasil operates.

In some departments, local governments are adopting more restrictive measures for the movement of people as a way to prevent the increase in cases. The vaccination has started in Brazil but so far only 2% of the population has been immunized.

Regarding the operation of the local partners, they all continue to partially offer remote activities and follow the health protocols of each municipality. Regarding the programmatic response, Childfund Brasil continues to deliver the food & hygiene kits and promote virtual educational and preventive actions with families and children.

Brazil has surpassed 11 million confirmed cases of coronavirus and 265 thousand deaths from the disease at the end of February. It added a million new diagnoses in 17 days. It was the shortest period in which the country accumulated this amount of infected people. The numbers are from the Ministry of Health. This increase in cases was expected as a result of the population's failure to respect the recommendations and protection measures, with a relaxation.

In early March, Brazil reached the mark of 8.7 million vaccinated against covid-19. In total, 8,736,891 Brazilians received at least one dose of vaccine, equivalent to 4.13% of the national population. The survey is from the consortium of press vehicles, based on information provided by the state health departments. In all, 2,975,266 people received the two doses of vaccine, following the recommendation of the laboratories that produce CoronaVac and Oxford / AstraZeneca. The number corresponds to only 1.41% of the Brazilian population.

The concern in all states has been the variation in the virus that has been diagnosed in some recent cases. Several regions, including the areas where ChildFund Brasil operates, are applying restrictive measures with partial lockdown in cities aiming at reducing the circulation of people by opening only establishments that are essential services. This period should last until the first half of March.

With regard to the operation of the local partners, they all continue to partially offer remote activities and follow the health protocols of each municipality. Regarding the programmatic response, Childfund Brasil continues to focus on the delivery the food & hygiene kits and promote virtual educational and preventive actions with families and children.

Consolidated official figures show that the country recorded, for the first time, more than 4 thousand deaths in 24 hours. The record leaves the authorities on alert. Brazil registers 40% of deaths by covid-19 in the world in one day.

Vaccination in Brazil goes reasonably well. So far, 22 million were immunized, representing 22% of the population. In absolute values, we are among the five that most vaccinate. Proportionally to the population, we have been doing better than other countries. The Brazilian government initially bet everything on a single vaccine: Oxford /AstraZeneca. The fact is that if it weren't for Butantan's agreement with Chinese Sinovac, we would have been left behind. It would have been better to bet on all of them, to reduce the risk.

Part of the difficulty in implementing effective social isolation comes from individual and collective, spontaneous or induced indiscipline. But there are two other variables, just as important. One is the movement of people whose work cannot be stopped and cannot be done remotely. The other is the workers who need to go out on the street so that people can stay at home. For example, the entire food production and distribution chain, as well as that of medicines. This is just to start.

Governments and experts debate ways to combat coronavirus mutations. Brazil has become a kind of laboratory for new strains. Variants of the virus threaten to prolong the pandemic.

The social vulnerability is getting worse for the poorest families as the government suspended the cash transfer program ot the families in the last three months, but it is confirmed with a smaller amount for the coming months.

Our Local Partners continue to partially offer remote activities and follow the health protocols of each municipality. As for the programmatic response, Childfund Brasil continues to focus on the delivery the food & hygiene kits and promote virtual educational and preventive actions with families and children.

* Host government posture: Have they declared a state of emergency and/or requested outside assistance? Which nationwide measures has the government taken, e.g., limitation on meetings, internal travel, school closures etc.

Yes. The Federal Government declared state of calamity. All the schools are closed, and agglomerations of people are prohibited. The local governments are monitoring the situation.

Some local governments are discussing about the possibility of re-opening gradually the segments of the market to restore the services. So far, most of the territories are demanding the population to use masks to walk on the streets. Most of the public spaces, such as schools, are still closed.

In some regions, the local governments are deciding to adopt restrict measures as an attempt to decrease contamination levels. The majority of schools were not fully reopened, and children are attending virtual classes. We continue to monitor closely.

* What responses has the government put into place to address the health crisis and/or the economic impact?

In additional to all the health protection actions determined by the Health Ministry, social and economic measures have been taken by the Federal Government to support the population focused on those who are benefited by the social programs and the labor market for the entrepreneurs and employees. The Government is expanding the number of beds in the health system by creating field hospitals (beds) in stadiums and event venues.

The Federal Government has launched a cash transfer program for the population that will provide for each family under the criteria of poverty situation R$600 (USD 115) and for individual entrepreneurs. Female heads of household will receive double. This amount will immediately be available and in the coming two months. The payment will be done through the current bank account number the families use to receive the benefit of the “Bolsa Família” Social Program via the official bank from the government.

In some regions, the local governments are imposing more restricted measures such as limiting time for walking on the streets and obliging the usage of masks for protection.

The cash transfer program launched by the Federal Government is supporting the population. However, some families are having difficult to access the benefit, especially those who do not have a bank account and has to go the bank to withdraw the money. We are providing, when possible, orientations to the families to help them get the money. This is only happening with families that are not benefited by the Bolsa Familia social program (regular social program offered by the government to the poorest families).

The federal government is anticipating the possibility of extending the cash transfer program for three months more, however, it still needs to be voted.

The federal government confirmed the extension of the cash transfer program for three months more. However, the amount will be reduced to half of what has been delivered to the families.

There were no additional measures taken by the government. The discussions are now concentrated on the vaccination.

December/20 was the last month that the population was granted with the cash transfer program support from the government.

The Government is planning to offer a cash transfer program support to the population for two or three months more, considering the need and more vulnerable families. It is still under discussion.

The Government confirmed to offer a cash transfer program support to the population for three months more, considering the need and more vulnerable families. This will be from April onwards.

* What travel restrictions has the government put in place for travelers entering the country?

The country has locked down land borders and passengers coming from other countries via airport are restricted

Brazil is reopening land borders but passengers coming from other countries via airport are still restricted.

Part 2: The Situation in Areas Where ChildFund Works

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partner Organization (Use Salesforce identifying code/name.) | # of Enrolled and Sponsored Children | | COVID19 Cases Reported in ChildFund Communities (Y/N/Unknown) Provide number if available. | Number of Enrolled Children Reported with COVID19 (If available.) | Number of enrolled children diseased as result of COVID19 |
| Sponsored | Enrolled |
| 9682 - ASCAI - Associação da Criança e Adolescente de Itaobim | 657 | 884 | 01 | 01 | 0 |
| 1736 - ASSOC COMMUNITARIA DE PADRE PARAISO | 454 | 543 | 01 | 0 | 0 |
| 4028 - Assoc Moradores Cariri Mirim | 211 | 240 | 0 | 03 | 0 |
| 1737 - ASSOCIACAO COMUNITARIA DE MEDINA | 889 | 1,155 | 0 | 0 | 0 |
| 1775 - ASSOCIACAO COMUNITARIA DO GUARANI | 305 | 354 | 0 | 0 | 0 |
| 3394 - ASSOCIACAO DAS FAMILIA DO PECEM | 354 | 748 | 0 | 0 | 0 |
| 1052 - ASSOCIACAO UNIDOS PARA O PROGRESSO | 810 | 1041 | 76 | 13 | 0 |
| 3176 - BADARO RURAL FAMILY HELPER PROJECT | 2,911 | 3,673 | 0 | 0 | 0 |
| 3392 - CENTRO DE APOIO A CRIANCA | 1,227 | 1,722 | 24 | 03 | 0 |
| 1733 - CONACREJE - CONS ASSOC CRECHES JEO | 526 | 735 | 1 | 0 | 0 |
| 1471 - CRIANCA FELIZ | 1139 | 1523 | 03 | 0 | 0 |
| 1458 - FRENTE BENEFICENTE PARA A CRIANCA | 905 | 1369 | 10 | 07 | 0 |
| 318 - GRUPO CRIANCA NOVA VIDA | 301 | 575 | 01 | 0 | 0 |
| 3862 - MINAS NOVAS FAMILY HELPER PROJECT | 368 | 429 | 02 | 0 | 0 |
| 3724 - MOV DE AJUDA FAMILIAR DE OCARA | 536 | 646 | 02 | 0 | 0 |
| 1613 - PROCAJ-DIAMANTINA | 906 | 1,125 | 01 | 01 | 0 |
| 1289 - PROJETO ALEGRIA DA CRIANCA | 1,260 | 1,565 | 02 | 0 | 0 |
| 4000 - PROSESC - Projeto Semear Esperanca de Carbonita | 807 | 1,034 | 01 | 0 | 0 |
| 427 - SOC DE EDUC E SAUDE A FAMILIA | 2,133 | 2,641 | 36 | 27 | 0 |
| 3393 - SOC PROM APOIO A FAMILIA ITAPIPOCA | 336 | 408 | 03 | 01 | 01 |
| 1766 - SOCIEDADE DE ASSISTENCIA A CRIANCA | 954 | 1,172 | 0 | 0 | 0 |
| 1451 - SORRISO DA CRIANCA | 654 | 846 | 0 | 0 | 0 |
| 3178 - TURMALINA FAMILY HELPER PROJECT | 952 | 1,294 | 0 | 0 | 0 |

Child death Information (the information was provided as regular sponsorship protocols)

Name: Jennifer Pereira Freire

ID:112044361

Child deaths: List any sponsored child (with Partner organization and child ID from salesforce) diseased as a result of COVID19. (Note: These need to be reported immediately following the regular sponsorship protocols.)

Three local partners (317, 1662, 2362) were disaffiliated in October/20 as originally planned.

Two local partners (3397 and 3729) were merged with 0427 in January/21 as originally planned.

Five local partners (3718, 3175, 3177, 3179, 3863) were merged with 3176 in March/21 as originally planned

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Partner Organization (Use Salesforce identifying code/name.) | What is the status of the program/sponsorship processes (operational/suspended)? | | | | | | |
| Program Implementation | CVS | M&E  Level 2 | Enrollment /Disaffiliation | Sponsorship Communication | DFC |
| 9682 - ASCAI - Associacao da Crianca e Adolescente de Itaobim | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1736 - ASSOC COMMUNITARIA DE PADRE PARAISO | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 4028 - Assoc Moradores Cariri Mirim | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1737 - ASSOCIACAO COMUNITARIA DE MEDINA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1775 - ASSOCIACAO COMUNITARIA DO GUARANI | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3394 - ASSOCIACAO DAS FAMILIA DO PECEM | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1052 - ASSOCIACAO UNIDOS PARA O PROGRESSO | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3176 - BADARO RURAL FAMILY HELPER PROJECT | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3392 - CENTRO DE APOIO A CRIANCA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1733 - CONACREJE - CONS ASSOC CRECHES JEO | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1471 - CRIANCA FELIZ | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1458 - FRENTE BENEFICENTE PARA A CRIANCA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 318 - GRUPO CRIANCA NOVA VIDA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3862 - MINAS NOVAS FAMILY HELPER PROJECT | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3724 - MOV DE AJUDA FAMILIAR DE OCARA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1613 - PROCAJ-DIAMANTINA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1289 - PROJETO ALEGRIA DA CRIANCA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 4000 - PROSESC - Projeto Semear Esperanca de Carbonita | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 427 - SOC DE EDUC E SAUDE A FAMILIA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3393 - SOC PROM APOIO A FAMILIA ITAPIPOCA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1766 - SOCIEDADE DE ASSISTENCIA A CRIANCA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 1451 - SORRISO DA CRIANCA | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |
| 3178 - TURMALINA FAMILY HELPER PROJECT | Operational (focus on initiatives related to prevention and protection including virtual environment) | Operational with limitations | Suspended | Operational with limitations | Operational with limitations | Operational with limitations |

Three LPs have been incorporated (9683 to 1337, 9202 to 3176 and 9182 to 3178) and one was disaffiliated (1058) as originally planned.

Note: As a global measure, all sponsor visits have been suspended.

* What issues are children in these areas facing (food shortages, safety concerns, schools’ closure, etc.)?

Protection issues and food shortage, Hygiene, basic care. Many children, adolescents and youths are reporting difficulties to participate in online classes due to lack of equipment such as computers, mobile phones and poor internet connection. In some regions, local governments are providing equipment and developing an online application that enable students to access the classes without internet fees.

* Child protection risks caused or exacerbated by crisis situation.

Children are kept in their homes and it could represent more vulnerability as their parents or caregivers are suffering stress caused by the quarantine.

Part 3: ChildFund’s Response

**3.a. Overall**

* Who is or will be leading/managing the response? Gabriel Barbosa, Program Manager
* How is ChildFund linked with humanitarian coordination structures, i.e., in which clusters or working groups do we participate? The most recent/next meeting and who is representing ChildFund? Donor meetings we have attended, or missions that we are aware of related to the response?

The Local Partners are in coordination with the government including Secretaries of Education, Secretary Health, Secretary of Social Assistance and local Councils to enhance and plan the interventions.

We are articulating with the local Governments the improvement of reporting mechanisms for situations of child violence via the current channels disk 100 (hotline) or website

There is also an articulation with Joining Forces Brazil to advocate for the provision of food from the government for the children as they are not attending school and consequently not having their meals.

As a result of the Advocacy articulated with other joining forces Organizations, disseminated a public statement on April 15th to become the law really effective with regard to the provision of food for the children as the schools are closed.

During the week from May 11th to May 18th, ChildFund Brasil has been promoting a series of lives and webinars related to the theme “Prevention of Sexual Abuse and Exploitation against Children”. This is part of the actions already planned related to the day of May 18th, when every year it is reminded about an emblematic case that happened in Brazil of a child who suffered sexual violence and was murdered. The actions were focused on our hashtag “I take care and take responsibility”.

ChildFund Brasil has promoted an on line festival (via youtube) called “Compassion Festival during the weekend (24th and 25th – June) with the participation of famous singers who dedicated 30 minutes each as volunteers to play songs and help us call to action for donations to the our campaign “nor virus, nor hunger: compassion):

Day 1 - <https://www.youtube.com/watch?v=D_7ES-9GLrg&t=5s>

Day 2 - <https://www.youtube.com/watch?v=mZaCJ_SEHsM>

ChilFund Brasil has been keeping on promoting online “Compassion Festival”, this time with the theme “the knowledge that touches our heart” with the inspirational lectures with three famous speakers for about 1 hour via a partnership with a company called DMT Palestras. It has supported us to leverage our brand and mobilize resources.

On May 28th, ChildFund Brasil promoted a Webinar via TEAMS to all our local partners to discuss about the importance of prevention and protecting children during this period of pandemic. The session was facilitated by a psychologist/expert in the thematic and moderated by ChildFund Brasil advisor.

On June 09th, ChildFund Brasil promoted a Webinar via TEAMS to all our local partners to discuss about the importance of “taking care of the caregivers” during this period of pandemic. The session was facilitated by a psychologist/expert in the thematic and moderated by ChildFund Brasil advisor.

ChildFund Brasil has promoted a second round of the on line festival (via youtube) called “Compassion Festival during the weekend (13th and 14th) with the participation of singers who dedicated 30 minutes each as volunteers to play songs and help us call to action for donations to the our campaign “nor virus, nor hunger: compassion):

Day 1: <https://www.youtube.com/watch?v=sxTH2GCfJ6c>

Day 2: <https://www.youtube.com/watch?v=zf1dU1js8_E>

ChildFund Brasil promoting a series of Webinar via TEAMS to all our local partners to discuss about the importance of “taking care of the caregivers” during this period of pandemic. There two sessions this month, on July 07th and 21st, facilitated by ChildFund Brasil advisor. Local Partner coordinators and educators are attending the sessions.

An initiative has been launched called “Dialogues on Poverty”, which is promoting a series of webinars about four main topics: *Income for the families*, *Health*, *Protection*, *Education*. We have completed a first series of four webinars with the participation of an expert to discuss about the theme, representation of all local partners and ChildFund Brasil staff.

ChildFund Brasil is keeping on promoting Webinars via TEAMS to all our local partners to discuss about the importance of “taking care of the caregivers” during this period of pandemic.

Another initiative was focused on Webinars about “Child and Adolescent Protection Network, a look at our reality” to mobilize our Local Partners on how to exchange experiences and good practices on Child protection interventions.

A Webinar was held on December 23 on Community-Based Child Protection to launch the publication Mapping Risk Factors and Protection of Children and Adolescents in Latin America on the YouTube of ChildFund Brazil.

ChildFund Brasil launched nationally through our Center of Social Intelligence in partnership with PUC University the Multidimensional index covering all the states of Brazil. It was relevant to leverage our recognition as well as position the organization as a reference in the area.

A second version of our Sustainable Social Transformation approach document was released including additional elements to support our intervention.

ChildFund Brasil provided a healthy and safe start to life for babies, in a more sustainable way by training pregnant women in child protection by enabling the integral development and well-being of their babies including the delivery of 45 baby cribs and baby wears.

A youth leader from our Youth Network (REJUDES) participated on March 8th in the “Girls Leading a More Equal World Event" with a valuable speech about her empowerment and contributions for the transformation of her community.

The local REJUDES committees have promoted a series of workshops about project management to the youths

ChildFund Brasil participated in the “Global Money Week” in partnership with an Institute called SICOOB with the representation of one specialist to discuss about social and finance skills.

**3.b. Program Response**

Please organize your program response report as per the 4 objectives included in our global response plan. You can add an additional category if you have response activities planned or executed that do not align with these objectives. For each objective use the questions below to guide your report.

* What kind of response activities or interventions have been executed? What support items are needed or have been collected/distributed?

1. Launch of our Resource Mobilization Campaign “Neither virus nor hunger: Compassion” - Kit Compassion (kit Compaixão)
2. Strengthening Child Protection and Advocacy initiatives (distribution of informative materials via WhatsApp to all families who have access to internet (approx. 70%)
3. ChildFund Brasil youth engagement through our REJUDES youth network

* What is the current progress of implementation vs. the established response plan?

We are expecting to deliver a kit Compaixão (Hygiene and foodstuff to 30.000 families and so far we have reached 11.718 (40%)

We have delivered 16.699 hygiene and foodstuff kits (Kits Compaixão) to the families (one to each enrolled family). It means 55% of the total 30.000 families.

We have delivered 17.365 kits Compaixão.

We have delivered a total of 18.403 kits Compaixão to the families (1038 within this reported period)

We have delivered a total of 20.866 kits Compaixão to the families (2.466 within this reported period)

We have delivered a total of 31.457 kits Compaixão to the families (8.599 within this reported period)

We have delivered a total of 44.172 kits Compaixão to the families (6.179 within this reported period)

We have delivered a total of 53.993 kits Compaixão to the families (8.906) within this reported period)

We have delivered a total of 56.352 kits Compaixão to the families (2.354) within this reported period)

We have delivered a total of 73.730 kits Compaixão to the families (17.378) within this reported period)

We have delivered a total of 86.781 kits Compaixão to the families (13.051) within this reported period)

We have delivered a total of 96.161 kits Compaixão to the families (9.308) within this reported period)

We have delivered a total of 104.342 kits Compaixão to the families (8.181) within this reported period)

We have delivered a total of 122,965kits Compaixão to the families (13,739) within this reported period)

We have delivered a total of 128,041kits Compaixão to the families (5,076) within this reported period)

We have delivered a total of 136,826kits Compaixão to the families (7,733) within this reported period)

We have delivered a total of 144,123kits of food and hygiene (Kit Compaixão) to the families (7,297) within this reported period)

* Who are we partnering or collaborating with to provide our response?

Local Partners, Secretaries of Education, Secretary Health, Secretary of Social Assistance Suppliers, Children’s Rights Councils, Community Volunteers, Youth Leaders,

* What kind of response activities are you still planning for the coming period?

1. Provide subsistence, comfort and relief to vulnerable families during the emergency (COVID-19)
2. Increase prevention, protection and emotional care measures with families during the emergency (COVID-19)
3. Engaging Youth from ChildFund Brasil against COVID-19

**3.b.1. Stop COVID-19 from infecting children and families**

**ChildFund’s Global Response Plan**

To help children and families protect themselves from COVID-19, we are installing community, handwashing stands; educating communities about symptoms, hygiene measures and where to get tested or treatment; and distributing soap, hand sanitizer, gloves and masks to families and frontline, health workers. For children who are being treated for COVID-19 or are subject to quarantine measures, we are creating child-friendly spaces with age-appropriate toys and reading matter.

* + Information & Prevention – Sharing useful information about contamination and orientation via social medias to the families; Social educators are also elaborating media content and interacting with children, adolescents and youths virtually; Weekly materials are being produced to be distributed to the families. Some local partners are promoting virtual storytelling for children facilitated by their social educators. They have also produced videos with content from our programmatic approach (social technology) Casinha de Cultura (games, individual and collective games.) so that children and families can, in their time of isolation, dedicate themselves to playing, the interaction between parents and children. Some workshops such as graffiti, ballet, dance, judo is happening via Youtube. This was an initiative taken by the teachers with aiming at keeping the connection with children and adolescents and allowing the continuity of activities even in times of social isolation.
  + In the region of Fortaleza and Cariri, we have delivered informative materials about hygiene to 1442 families and 932 educative games to families and children to help them receiving quality information about the virus and having some fun together.
  + 1792 families received informative materials about COVID-19 within their Foodstuff and Hygiene Kits and 1555 online materials

**3.b.2. Ensure that children get food they need**

**ChildFund’s Global Response Plan**

To ensure that the most vulnerable families can keep food on the table, pay rent and cover other basic needs, we are providing cash for those families most needing this support, such as those who have lost their income because of COVID-19, child or elder-headed households, and/or households affected by disability or chronic illness. Where possible, we are distributing food and basic household items directly, carefully abiding by COVID-19 protection measures

**3.b.2. 1.** *Cash Transfers and vouchers*

-Is your CO planning or implementing cash transfers or vouchers as part of COVID19 response? ChildFund Brasil is delivering food kits instead of providing vouchers for cash transfers. ChildFund Brasil received a donation of 1000 cards (vouchers) to be delivered to the families to be used to buy the food kit

- If so, brief description of progress to date.

***Cash transfers or vouchers executed***

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Beneficiaries** | | | **Amount transferred (US$)** | **Transfer mechanism (i.e. mobile money, banking system other financial service provider etc,** |
| *Total* | *Gender (if available)* | |
|  | Female | Male |  |  |
| 34,919 | N/A | N/A | US$ 698,380 | Cards (vouchers) |

Only in March/21: 5,811

**3.b.2.2.** *Other responses in relation to objective 3.b.2.*

Delivery of 20.866 kits Compaixão (one for each enrolled family). 2.466 within this reported period.

Delivery of 31.457 kits Compaixão (one for each enrolled family). 7.032 within this reported period.

Delivery of 53.993 kits Compaixão (two to each enrolled family for the period). 8.906 within this reported period.

Delivery of 73.730 kits Compaixão. 17.378 within this reported period.

Delivery of 86.781 kits Compaixão. 13.051 within this reported period

Delivery of 96.161 kits Compaixão. 9.308 within this reported period

Delivery of 104.342 kits Compaixão. 8.181 within this reported period

Delivery of 110.927 kits Compaixão. 6.585 within this reported period

Delivery of 122,965 kits Compaixão. 13,739 within this reported period

Delivery of 136,826 kits Compaixão. 7,733 within this reported period

Delivery of 144,123 food and hygiene kits. 7,297 within this reported period

**3.b.3. Keep children safe from Violence: physically and emotionally**

**ChildFund’s Global Response Plan**

We are supporting community-based child protection systems that identify, respond to and refer cases of abuse, neglect, violence or exploitation. We are also providing virtual, online psychological first aid and counseling, and supporting temporary shelters for children who live on the street, providing hygiene supplies, food and other basics. We are also arranging safe and appropriate care for children who are separated from their caregivers due to treatment or prevention measures.

* + There is also an articulation with Joining Forces Brazil to advocate for the provision of food from the government for the children as they are not attending school and consequently not having their meals
  + ChildFund Brasil is keeping the articulations with the local Governments the improvement of reporting mechanisms for situations of child violence via the current channels disk 100 (hotline) or website
  + Participation in strategic discussions and meetings with key organizations and local governments to explore any synergy opportunity for the response
  + Dissemination of informative materials about child protection and prevention of abuse in domestic environments; In some cases, we have included the informative materials within the hygiene and foodstuff kits
  + 10.680 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 1.381 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 6.227 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 517 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 12.533 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 3.599 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 15.182 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 3.338 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 04 cases involving suspicion of child abuse were reported to the LPs and 03 of them addressed to the local children’s council
  + 13.427 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 6520 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 12.118 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 6.763 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 02 cases involving suspicion of child abuse were reported to the LPs and 01 of them addressed to the local children’s council
  + 14.733 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 5368 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 10.367 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 4.876 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 02 cases involving suspicion of child abuse were reported to the LPs and 02 of them addressed to the local children’s council
  + 14.433 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 1926 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 10.179 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 895 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + No cases involving suspicion of child abuse were reported by the LPs
  + 15.411 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 3.936 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 10.920 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 3.798 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 04 cases involving suspicion of child abuse were reported to the LPs and 04 of them addressed to the local children’s council
  + 15.890 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 6.488 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 9.487 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 4.181 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 05 cases involving suspicion of child abuse were reported to the LPs and 05 of them addressed to the local children’s council
  + 15.680 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 2.542 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 10.534 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 1.696 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + No cases involving suspicion of child abuse were reported to the LPs
  + 14.651 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 1.258 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 8.496 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 1.107 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 13 cases involving suspicion of child abuse were reported to the LPs and addressed to the local children’s council
  + 16.406 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 4.735 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 10.904 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 3.863 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 04 cases involving suspicion of child abuse were reported to the LPs and 03 addressed to the local children’s council
  + 16.533 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 9.524 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 11.261 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 6.955 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 10 cases involving suspicion of child abuse were reported to the LPs and addressed to the local children’s council
  + 23.691 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 8.675 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 14.158 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 1.941 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 10 cases involving suspicion of child abuse were reported to the LPs and addressed to the local children’s council
  + 20.153 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 9.971 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 12.369 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 2.670 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 14 cases involving suspicion of child abuse were reported to the LPs and addressed to the local children’s council
  + 19,096 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 10,148 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 11,516 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 5,681 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 06 cases involving suspicion of child abuse were reported to the LPs and 04 addressed to the local children’s council
  + 18,972 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 6,033 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 9,161 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 4,586 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 03 cases involving suspicion of child abuse were reported to the LPs and 03 addressed to the local children’s council
  + 16,003 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 1,798 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 9,502 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 561 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 01 case involving suspicion of child abuse was reported to the LPs and addressed to the local children’s council
  + 18,171 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 890 families received printed materials about child violence prevention, recreational activities for children and families and self-care;
  + 12,041 families informed about child protection mechanisms and hot line channels to report cases of violence;
  + 557 families received printed materials about child protection mechanisms and hot line channels to report cases of violence;
  + 01 case involving suspicion of child abuse was reported to the LPs and addressed to the local children’s council
  + 19,560 families were informed via WhatsApp about the importance of child violence prevention, recreational activities for children and families and self-care;
  + 3,258 families received printed materials about child violence prevention, recreational activities for children and families and self-care
  + 11,491 families informed about child protection mechanisms and hot line channels to report cases of violence
  + 1,105 families received printed materials about child protection mechanisms and hot line channels to report cases of violence
  + 06 case involving suspicion of child abuse was reported to the LPs and addressed to the local children’s council

**3.b.4. Help children continue to do their job: Learning**

**ChildFund’s Global Response Plan**

While schools remain closed, we are supporting children’s learning through activities and tutoring sessions online or by radio. For students without reliable internet access, we are distributing home learning kits with materials and guides for their use.

ChildFund Brasil is supporting the local partners to offer online activities to the children, including workshops on hygiene, storytelling and other activities to support the families and their children. In some cases, we are distributing educative games to children included in the food and hygiene kits.

* + 300 youths participated in online courses and lives about youth rights
  + 931 youths participated in debates and lives about entrepreneurship and income generation
  + 670 youths participated in online courses and lives about youth rights
  + 643 youths participated in debates and lives about entrepreneurship and income generation
  + 1.244 youths participated in online courses and lives about youth rights
  + 1.043 youths participated in debates and lives about entrepreneurship and income generation
  + 492 youths participated in online courses and lives about youth rights
  + 837 youths participated in debates and lives about entrepreneurship and income generation
  + 486 youths participated in online courses and lives about youth rights
  + 1174 youths participated in debates and lives about entrepreneurship and income generation
  + 785 youths participated in online courses and lives about youth rights
  + 1.539 youths participated in debates and lives about entrepreneurship and income generation
  + 907 youths participated in online courses and lives about youth rights
  + 1.342 youths participated in debates and lives about entrepreneurship and income generation
  + 719 youths participated in online courses and lives about youth rights
  + 1.015 youths participated in debates and lives about entrepreneurship and income generation
  + 876 youths participated in online courses and lives about youth rights
  + 1.516 youths participated in debates and lives about entrepreneurship and income generation
  + 613 youths participated in online courses and lives about youth rights
  + 1.154 youths participated in debates and lives about entrepreneurship and income generation
  + 808 youths participated in online courses and lives about youth rights
  + 1.609 youths participated in debates and lives about entrepreneurship and income generation
  + 895 youths participated in online courses and lives about youth rights
  + 1.437 youths participated in debates and lives about entrepreneurship and income generation
  + 501 youths participated in online courses and lives about youth rights
  + 1.805 youths participated in debates and lives about entrepreneurship and income generation
  + 659 youths participated in online courses and lives about youth rights
  + 2,168 youths participated in debates and lives about entrepreneurship and income generation
  + 365 youths participated in online courses and lives about youth rights
  + 726 youths participated in debates and lives about entrepreneurship and income generation
  + 741 youths participated in online courses and lives about youth rights
  + 1,610 youths participated in debates and lives about entrepreneurship and income generation
  + 792 youths participated in online courses and lives about youth rights
  + 1,876 youths participated in debates and lives about entrepreneurship and income generation

**3.b.5. Other responses**

* + From our child protection mechanisms, we have selected some approaches and dynamics for the prevention of abuse in domestic environments, such as: playing with the family, attention to a safe home and building healthy family bonds. This content is being disseminated through social media (WhatsApp, Instagram and Facebook), community radio stations and when possible visits to families during the delivery of the Compassion Kit (Kit Compaixão). We are also working in a network to defend the prioritization of public resources for the feeding of children and the improvement of reporting mechanisms for situations of child violence.
  + Our local partners have submitted 77 proposals to mobilize resources and 33 were granted to get additional foodstuff kits to be distributed to the families; They have also distributed 2613 PPE equipment (masks) to the families;
  + Our local partners have submitted 40 proposals to mobilize resources and 09 were granted to get additional 1000 foodstuff kits (in addition to the kits compaixão) to be distributed to the families;
  + 605 informative materials about COVID-19 were distributed via social media to the families;
  + 2205 families received printed informative materials about COVID-19;
  + 704 families received PPE equipment (masks);
  + 705 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 5.738 received online material about COVID-19 prevention
  + Our local partners have submitted 43 proposals to mobilize resources and 17 were granted to get additional 1463 foodstuff kits (in addition to the kits compaixão) to be distributed to the families;
  + 694 informative materials about COVID-19 were distributed via social media to the families;
  + 3734 families received printed informative materials about COVID-19;
  + 1152 families received PPE equipment (masks);
  + 1119 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.325 received online material about COVID-19 prevention
  + Our local partners have submitted 42 proposals to mobilize resources and 22 were granted to get additional 2.208 foodstuff kits (in addition to the kits compaixão) to be distributed to the families;
  + 1680 informative materials about COVID-19 were distributed via social media to the families;
  + 7344 families received printed informative materials about COVID-19;
  + 2615 families received PPE equipment (masks);
  + 865 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.036 received online material about COVID-19 prevention
  + Our local partners have submitted 37 proposals to mobilize resources and 19 were granted to get additional 2.522 foodstuff kits (in addition to the kits compaixão) to be distributed to the families;
  + 959 informative materials about COVID-19 were distributed via social media to the families;
  + 5618 families received printed informative materials about COVID-19;
  + 817 PPE equipment (masks, gloves); delivered to the families
  + 976 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.714 received online material about COVID-19 prevention
  + Our local partners have submitted 31 proposals to mobilize resources and 14 were granted to get additional 991 foodstuff kits (in addition to the kits compaixão) to be distributed to the families;
  + 809 informative materials about COVID-19 were distributed via social media to the families;
  + 2964 families received printed informative materials about COVID-19;
  + 1260 PPE equipment (masks, gloves); delivered to the families
  + 1.423 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.810 received online material about COVID-19 prevention
  + Our local partners have submitted 10 proposals to mobilize resources and 05 were granted to get additional 2334 foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 1324 informative materials about COVID-19 were distributed via social media to the families;
  + 5072 families received printed informative materials about COVID-19;
  + 728 PPE equipment (masks, gloves); delivered to the families
  + 994 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.411 received online material about COVID-19 prevention
  + Our local partners have submitted 12 proposals to mobilize resources and 07 were granted to get additional 3072 foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 2.133 informative materials about COVID-19 were distributed via social media to the families;
  + 5.479 families received printed informative materials about COVID-19;
  + 1.740 PPE equipment (masks, gloves); delivered to the families
  + 972 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.519 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 56 proposals to mobilize resources and 59 (including previous ones) were granted to get additional 2.997 foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 1.348 informative materials about COVID-19 were distributed via social media to the families;
  + 2.878 families received printed informative materials about COVID-19;
  + 129 PPE equipment (masks, gloves); delivered to the families
  + 1.142 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.574 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 09 proposals to mobilize resources and 07 were granted to get additional 1.492 foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 288 informative materials about COVID-19 were distributed via social media to the families;
  + 1.710 families received printed informative materials about COVID-19;
  + 351 PPE equipment (masks, gloves); delivered to the families
  + 1.173 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.355 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 27 new proposals to mobilize resources and 34 were granted (including previous ones submitted) to get additional foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 5.297 informative materials about COVID-19 were distributed via social media to the families;
  + 6.700 families received printed informative materials about COVID-19;
  + 6.228 PPE equipment (masks, gloves); delivered to the families
  + 1.352 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.820 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 26 new proposals to mobilize resources and 15 were granted (including previous ones submitted) to get additional foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 3.909 informative materials about COVID-19 were distributed via social media to the families;
  + 10.552 families received printed informative materials about COVID-19;
  + 2.400 PPE equipment (masks, gloves); delivered to the families
  + 1.132 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.625 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 19 new proposals to mobilize resources and 17 were granted (including previous ones submitted) to get additional foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 1.794 informative materials about COVID-19 were distributed via social media to the families;
  + 6.367 families received printed informative materials about COVID-19;
  + 2.424 PPE equipment (masks, gloves); delivered to the families
  + 2.048 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.693 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 40 new proposals to mobilize resources and 26 were granted (including previous ones submitted) to get additional foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 2.453 informative materials about COVID-19 were distributed via social media to the families;
  + 4.567 families received printed informative materials about COVID-19;
  + 4.789 PPE equipment (masks, gloves); delivered to the families
  + 1.332 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 3.918 youth leaders received online material about COVID-19 prevention
  + Our local partners have submitted 31 new proposals to mobilize resources and 16 were granted (including previous ones submitted) to get additional foodstuff kits (in addition to the kits Compaixão) to be distributed to the families;
  + 2,497 informative materials about COVID-19 were distributed via social media to the families;
  + 5,340 families received printed informative materials about COVID-19;
  + 1,296 PPE equipment (masks, gloves); delivered to the families
  + 1.332 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 1,771 youth leaders received online material about COVID-19 prevention
  + 5,020 informative materials about COVID-19 were distributed via social media to the families;
  + 9,715 families received printed informative materials about COVID-19;
  + 3,147 PPE equipment (masks, gloves); delivered to the families
  + 976 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 2,423 youth leaders received online material about COVID-19 prevention
  + 221 informative materials about COVID-19 were distributed via social media to the families;
  + 1,472 families received printed informative materials about COVID-19;
  + 4.732 PPE equipment (masks, gloves); delivered to the families
  + 413 youth leaders from our REJUDES network involved in online interventions and supporting the local partners;
  + 2,173 youth leaders received online material about COVID-19 prevention
  + 424 informative materials about COVID-19 were distributed via social media to the families
  + 1,417 families received printed informative materials about COVID-19
  + 476 PPE equipment (masks, gloves); delivered to the families
  + 799 youth leaders from our REJUDES network involved in online interventions and supporting the local partners
  + 2,776 youth leaders received online material about COVID-19 prevention
  + 1,362 informative materials about COVID-19 were distributed via social media to the families
  + 1,802 families received printed informative materials about COVID-19
  + 1,343 PPE equipment (masks, gloves); delivered to the families
  + 462 youth leaders from our REJUDES network involved in online interventions and supporting the local partners
  + 3,238 youth leaders received online material about COVID-19 prevention

**Below Sections for Internal Use Only**

Part 4: Office and Staff Status

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Office Status (Open/Closed) | Number of Staff: 55 | | | | |
| Diagnosed with COVID19 | Diseased from COVID19 | Working from Office | Working from Home | On Special Leave |
| Closed (Team is working home office) | 9 | 0 | 5 (part-time) | 55 | 0 |

Notes:

* Any cases of staff diseased need to be reported immediately to RD and GHR. No
* Special leave as per [COVID19 Administrative Guidelines](https://childfundintl.sharepoint.com/:b:/g/News/COVID-19/ETFAT1mC_8BHjamXXOqMs3gBRsmi2thcbUO4qLhyddl4kA?e=zYbNiC). No

Number of staff/partner organization staff completed WHO COVID online training <https://www.who.int/emergencies/diseases/novel-coronavirus-2019/training/online-training>.

None reported

Part 5 Human Resources

* Which visitors are there in the country ? Please include names, functions, contact information and arrival/departure dates for both IO and RO staff (note: due to the travel ban, this will apply only once the ban has been lifted) None
* Any gaps in staffing/need for deployment from other Cos or Global Teams? None
* Are there any other major HR issues?

ChildFund Brasil office is operating in accordance with the government decrees including health measures to be adopted and office closure. So far, the majority of team members are working from their homes. Only administrative and sponsorship departments are working respecting all the sanitary recommendations and number of staff members present in the office.

Part 6 Safety & Security

* Are police and other services functioning in the normal manner?

Yes

* Are the courts still operating?

Yes

* Are there reports of looting or increased criminality?

No

* Have military personal being deployed to patrol towns or cities?

Just to support health system in specific areas

* Confirm the safety of staff and their families in the affected area.
* Have Safety and security risks/mitigation plans been updated to current environment? Not completed
* Recommendations around any upcoming travel planned for staff or donors (note: Only once global travel ban has been lifted)

Part 7 Grants

List all active grants:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Grant Job Code | Grant Name | Donor | Status of Implementation (Normal/Reduced/Suspended) | Any specific guidance received from donor? (Yes/No) |
|  | Agua Pura para Crianças | Procter&Gamble | Reduced | No |

Provide any additional narrative on how the COVID19 crisis affects implementation of your major grants.

The Agua Pura para Crianças Project is operation under significant reduction. At this point, the local partners are coordinating only the delivery of P&G sachets for water purification. Our team made available for distribution 294.000 for the benefitted families which will use it for approximately three months. So far, we have distributed 354.000 sachets.

We have distributed 1.590.720 sachets to the families.

Part 8 Funding

Provide information about potential sources of funding, including grant donors, subsidy, Emergency Action Fund, Alliance members, GIK, etc., for these emergency response efforts using the chart below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Donor** | **Program** | **Amount (USD)** | **Requested? (Y/N)** | **Confirmed? (Y/N)** |
| On line Campaign  <https://childfundbrasil.colabore.org/covid/single_step> | Hygiene and Foodstuff kits | 687,000 | 687,000 | 49,000 |

**Official accounting exchange rate (5,3250)**

* Budget
  + Outline how we will use this funding with a rough topline budget.

This will be fully used to buy and deliver food and hygiene kits to the families

ChildFund Brasil received a donation of 3,3 tons of protein (chicken) from a private company/industry called JBS to be distributed (included in the kits) via one local partner to benefit 1646 families.

The JBS group confirmed a donation to ChildFund Brasil of an amount of R$ 100 (USD 20) to be delivered to 1.000 families and used to provide food and hygiene kits. This will be delivered to the families via our local partners using vouchers. Moreover, they have approved a project of approximately USD 80.000 to support 1.000 families with a sustainable project of chicken and horticulture. They will pay directly to the providers.

ChildFund Brasil together with two huge Brazilian Organizations – CUFA and Gerando Falcões launched a national challenge that intends to engage 10 million young people to raise funds needed to feed 10 million families who are suffering more heavily from the consequences of the economic crisis caused by the COVID-19 pandemic. This is the main objective of the 10x10 Challenge. Launched on June 22, the 10x10 Challenge will last 30 days and transform the Brazilian internet in a great virtual gymkhana with youth as protagonist. In the first week, several of the biggest gamers and youtubers in Brazil will mobilize their communities of fans and followers to raise funds for the acquisition of digital food baskets for benefited families. <https://desafio10x10.com.br/>

ChildFund Brasil has made an alliance with Ticket Endered Brasil for the issuance of cards (vouchers) without costs for some local partners who wish to use this method of delivery for families with digital vouchers

ChildFund Brasil made an alliance and signed an agreement with World Food Program to support us in the overcoming of extreme poverty and prospect jointly donors.

ChildFund Brasil received a donation 400 shoes for boys and girls from a factory called 4J.

ChildFund Brasil delivered 750 vouchers received from the World Food Program.

ChildFund Brasil delivered 450 vouchers received from the World Food Program.

Part 9 Media/Communications

* + List of media who will be or have been contacted with press releases.

There were at least 03 TV news and written articles in websites about our initiative to help the families. One of them is showing the local partner as an example of organization and excellence to deliver the kits to the families

02 publication (articles) in local newspaper about our Campaign Nor Virus, Nor hunger: Compassion

A series of lives have been promoted via our institutional Instagram about our campaign, cause and purpose.

ChildFund Brasil has been promoted during an important three day event of priests in

Brazil (CTPI) to mobilize resources for our campaigns a well as for new sponsors. This was an online meeting.

We have also developed a land page in our Website to share our interventions with local and international sponsors.

National influencers (social media) have engaged with ChildFund Brasil to help us leverage our cause in the across the country and mobilize resources.

* + List of emergency CO spokespeople, including name, location, contact information, and languages spoken.

Gerson Pacheco – [gersonpacheco@childfundbrasil.org.br](mailto:gersonpacheco@childfundbrasil.org.br) , Portuguese, English and Spanish

* + Plans for collecting photos/videos/stories, e.g., should an outside photographer be hired? Not yet
  + Key points for messaging and visibility, particularly any host-government sensibilities that must be considered. No
* Support needed or requested from IO, GSS or Global Teams – whether onsite or remote.

So far, in this phase, ChildFund Brasil is operating with local resources but certainly will need support in the coming phases